## Raw_Cost_Ledger
Invoice_No | Month | Trade | Cost_Code | Description | Contractor | PO_Number | Planned_Cost | Actual_Cost | Status | Approved_By
INV-CIV-01-2824 | Jan-24 | Civil | CI-01 | Site Preparation & Clearing | Judlau Contracting | PO-13278 | 88640 | 100835.4 | Posted | R. Okafor
INV-CIV-02-5012 | Feb-24 | Civil | CI-01 | Site Preparation & Clearing | Judlau Contracting | PO-39256 | 110800 | 113213.93 | Posted | A. Chen
INV-CIV-03-2679 | Mar-24 | Civil | CI-01 | Site Preparation & Clearing | Judlau Contracting | PO-98696 | 132960 | 138876.11 | Posted | J. Martinez
INV-CIV-04-7912 | Apr-24 | Civil | CI-01 | Site Preparation & Clearing | Judlau Contracting | PO-14165 | 177280 | 194588.33 | Posted | J. Martinez
INV-CIV-05-2535 | May-24 | Civil | CI-01 | Site Preparation & Clearing | Judlau Contracting | PO-38657 | 243760 | 266958.08 | Posted | A. Chen
INV-CIV-06-9279 | Jun-24 | Civil | CI-01 | Site Preparation & Clearing | Judlau Contracting | PO-88907 | 288080 | 321366.49 | Posted | J. Martinez
INV-CIV-07-4257 | Jul-24 | Civil | CI-01 | Site Preparation & Clearing | Judlau Contracting | PO-95181 | 288080 | 275129.31 | Posted | S. Patel
INV-CIV-08-4611 | Aug-24 | Civil | CI-01 | Site Preparation & Clearing | Judlau Contracting | PO-68878 | 265920 | 264079.37 | Posted | R. Okafor
INV-CIV-09-1106 | Sep-24 | Civil | CI-01 | Site Preparation & Clearing | Judlau Contracting | PO-30926 | 221600 | 221411.43 | Posted | S. Patel
INV-CIV-10-6574 | Oct-24 | Civil | CI-01 | Site Preparation & Clearing | Judlau Contracting | PO-46421 | 177280 | 0 | Forecast | A. Chen
INV-CIV-11-4527 | Nov-24 | Civil | CI-01 | Site Preparation & Clearing | Judlau Contracting | PO-54118 | 132960 | 0 | Forecast | J. Martinez
INV-CIV-12-2519 | Dec-24 | Civil | CI-01 | Site Preparation & Clearing | Judlau Contracting | PO-59797 | 88640 | 0 | Forecast | J. Martinez
INV-CIV-01-6635 | Jan-24 | Civil | CI-02 | Earthworks & Grading | Tully Construction | PO-89131 | 55320 | 59412.33 | Posted | R. Okafor
INV-CIV-02-1711 | Feb-24 | Civil | CI-02 | Earthworks & Grading | Tully Construction | PO-70217 | 69150 | 74087.29 | Posted | J. Martinez
INV-CIV-03-7201 | Mar-24 | Civil | CI-02 | Earthworks & Grading | Tully Construction | PO-20328 | 82980 | 85595.74 | Posted | R. Okafor
INV-CIV-04-6925 | Apr-24 | Civil | CI-02 | Earthworks & Grading | Tully Construction | PO-85674 | 110640 | 117733.35 | Posted | A. Chen
INV-CIV-05-2139 | May-24 | Civil | CI-02 | Earthworks & Grading | Tully Construction | PO-16006 | 152130 | 174854.79 | Posted | A. Chen
INV-CIV-06-5741 | Jun-24 | Civil | CI-02 | Earthworks & Grading | Tully Construction | PO-20458 | 179790 | 204082.96 | Posted | A. Chen
INV-CIV-07-2654 | Jul-24 | Civil | CI-02 | Earthworks & Grading | Tully Construction | PO-59823 | 179790 | 182483.37 | Posted | R. Okafor
INV-CIV-08-8428 | Aug-24 | Civil | CI-02 | Earthworks & Grading | Tully Construction | PO-93320 | 165960 | 161361.39 | Posted | R. Okafor
INV-CIV-09-3664 | Sep-24 | Civil | CI-02 | Earthworks & Grading | Tully Construction | PO-58520 | 138300 | 131408.45 | Posted | R. Okafor
INV-CIV-10-4432 | Oct-24 | Civil | CI-02 | Earthworks & Grading | Tully Construction | PO-97841 | 110640 | 0 | Forecast | R. Okafor
INV-CIV-11-2169 | Nov-24 | Civil | CI-02 | Earthworks & Grading | Tully Construction | PO-89840 | 82980 | 0 | Forecast | A. Chen
INV-CIV-12-9751 | Dec-24 | Civil | CI-02 | Earthworks & Grading | Tully Construction | PO-42087 | 55320 | 0 | Forecast | A. Chen
INV-CIV-01-7216 | Jan-24 | Civil | CI-03 | Dewatering Works | Tully Construction | PO-45382 | 51200 | 58661.18 | Posted | A. Chen
INV-CIV-02-6313 | Feb-24 | Civil | CI-03 | Dewatering Works | Tully Construction | PO-17331 | 64000 | 67433.99 | Posted | A. Chen
INV-CIV-03-1525 | Mar-24 | Civil | CI-03 | Dewatering Works | Tully Construction | PO-51347 | 76800 | 78823.74 | Posted | S. Patel
INV-CIV-04-5386 | Apr-24 | Civil | CI-03 | Dewatering Works | Tully Construction | PO-18675 | 102400 | 113865.06 | Posted | A. Chen
INV-CIV-05-6155 | May-24 | Civil | CI-03 | Dewatering Works | Tully Construction | PO-37869 | 140800 | 147668.61 | Posted | S. Patel
INV-CIV-06-7482 | Jun-24 | Civil | CI-03 | Dewatering Works | Tully Construction | PO-94259 | 166400 | 187867.41 | Posted | S. Patel
INV-CIV-07-3340 | Jul-24 | Civil | CI-03 | Dewatering Works | Tully Construction | PO-44718 | 166400 | 159887.85 | Posted | A. Chen
INV-CIV-08-5040 | Aug-24 | Civil | CI-03 | Dewatering Works | Tully Construction | PO-83579 | 153600 | 154795.54 | Posted | R. Okafor
INV-CIV-09-8019 | Sep-24 | Civil | CI-03 | Dewatering Works | Tully Construction | PO-86484 | 128000 | 124334 | Posted | S. Patel
INV-CIV-10-6930 | Oct-24 | Civil | CI-03 | Dewatering Works | Tully Construction | PO-38746 | 102400 | 0 | Forecast | A. Chen
INV-CIV-11-9348 | Nov-24 | Civil | CI-03 | Dewatering Works | Tully Construction | PO-74686 | 76800 | 0 | Forecast | J. Martinez
INV-CIV-12-1771 | Dec-24 | Civil | CI-03 | Dewatering Works | Tully Construction | PO-24371 | 51200 | 0 | Forecast | A. Chen
INV-CIV-01-3621 | Jan-24 | Civil | CI-04 | Underground Utilities | Judlau Contracting | PO-99192 | 51200 | 57715.59 | Posted | S. Patel
INV-CIV-02-2040 | Feb-24 | Civil | CI-04 | Underground Utilities | Judlau Contracting | PO-60432 | 64000 | 68156.88 | Posted | S. Patel
INV-CIV-03-8668 | Mar-24 | Civil | CI-04 | Underground Utilities | Judlau Contracting | PO-79352 | 76800 | 79338.33 | Posted | R. Okafor
INV-CIV-04-1188 | Apr-24 | Civil | CI-04 | Underground Utilities | Judlau Contracting | PO-99166 | 102400 | 119269.51 | Posted | J. Martinez
INV-CIV-05-9797 | May-24 | Civil | CI-04 | Underground Utilities | Judlau Contracting | PO-44973 | 140800 | 159141.26 | Posted | R. Okafor
INV-CIV-06-2827 | Jun-24 | Civil | CI-04 | Underground Utilities | Judlau Contracting | PO-48469 | 166400 | 188412.08 | Posted | S. Patel
INV-CIV-07-3591 | Jul-24 | Civil | CI-04 | Underground Utilities | Judlau Contracting | PO-69470 | 166400 | 170308.85 | Posted | J. Martinez
INV-CIV-08-5315 | Aug-24 | Civil | CI-04 | Underground Utilities | Judlau Contracting | PO-75612 | 153600 | 153811.21 | Posted | A. Chen
INV-CIV-09-9317 | Sep-24 | Civil | CI-04 | Underground Utilities | Judlau Contracting | PO-23947 | 128000 | 132065.99 | Posted | R. Okafor
INV-CIV-10-9317 | Oct-24 | Civil | CI-04 | Underground Utilities | Judlau Contracting | PO-89818 | 102400 | 0 | Forecast | A. Chen
INV-CIV-11-3504 | Nov-24 | Civil | CI-04 | Underground Utilities | Judlau Contracting | PO-59009 | 76800 | 0 | Forecast | A. Chen
INV-CIV-12-9837 | Dec-24 | Civil | CI-04 | Underground Utilities | Judlau Contracting | PO-79514 | 51200 | 0 | Forecast | J. Martinez
INV-CIV-01-6310 | Jan-24 | Civil | CI-05 | Piling & Foundations | Judlau Contracting | PO-74042 | 172160 | 185709.92 | Posted | J. Martinez
INV-CIV-02-2832 | Feb-24 | Civil | CI-05 | Piling & Foundations | Judlau Contracting | PO-57576 | 215200 | 221177 | Posted | R. Okafor
INV-CIV-03-4923 | Mar-24 | Civil | CI-05 | Piling & Foundations | Judlau Contracting | PO-17592 | 258240 | 262929.01 | Posted | A. Chen
INV-CIV-04-2290 | Apr-24 | Civil | CI-05 | Piling & Foundations | Judlau Contracting | PO-21226 | 344320 | 376365.17 | Posted | S. Patel
INV-CIV-05-2133 | May-24 | Civil | CI-05 | Piling & Foundations | Judlau Contracting | PO-79822 | 473440 | 514986.49 | Posted | A. Chen
INV-CIV-06-3103 | Jun-24 | Civil | CI-05 | Piling & Foundations | Judlau Contracting | PO-96474 | 559520 | 592988 | Posted | S. Patel
INV-CIV-07-3705 | Jul-24 | Civil | CI-05 | Piling & Foundations | Judlau Contracting | PO-44741 | 559520 | 569022.54 | Posted | S. Patel
INV-CIV-08-4470 | Aug-24 | Civil | CI-05 | Piling & Foundations | Judlau Contracting | PO-80686 | 516480 | 504839.25 | Posted | A. Chen
INV-CIV-09-6107 | Sep-24 | Civil | CI-05 | Piling & Foundations | Judlau Contracting | PO-62296 | 430400 | 416761.71 | Posted | R. Okafor
INV-CIV-10-8177 | Oct-24 | Civil | CI-05 | Piling & Foundations | Judlau Contracting | PO-77839 | 344320 | 0 | Forecast | S. Patel
INV-CIV-11-2982 | Nov-24 | Civil | CI-05 | Piling & Foundations | Judlau Contracting | PO-42493 | 258240 | 0 | Forecast | A. Chen
INV-CIV-12-2049 | Dec-24 | Civil | CI-05 | Piling & Foundations | Judlau Contracting | PO-54313 | 172160 | 0 | Forecast | J. Martinez
INV-CIV-01-4770 | Jan-24 | Civil | CI-06 | Site Roads & Hardstanding | Judlau Contracting | PO-87128 | 106160 | 119939.92 | Posted | A. Chen
INV-CIV-02-1117 | Feb-24 | Civil | CI-06 | Site Roads & Hardstanding | Judlau Contracting | PO-19305 | 132700 | 135611.17 | Posted | J. Martinez
INV-CIV-03-4750 | Mar-24 | Civil | CI-06 | Site Roads & Hardstanding | Judlau Contracting | PO-18834 | 159240 | 174989 | Posted | J. Martinez
INV-CIV-04-6413 | Apr-24 | Civil | CI-06 | Site Roads & Hardstanding | Judlau Contracting | PO-19287 | 212320 | 226156.63 | Posted | A. Chen
INV-CIV-05-5562 | May-24 | Civil | CI-06 | Site Roads & Hardstanding | Judlau Contracting | PO-97684 | 291940 | 336769.59 | Posted | S. Patel
INV-CIV-06-4510 | Jun-24 | Civil | CI-06 | Site Roads & Hardstanding | Judlau Contracting | PO-80678 | 345020 | 384401.78 | Posted | A. Chen
INV-CIV-07-8744 | Jul-24 | Civil | CI-06 | Site Roads & Hardstanding | Judlau Contracting | PO-41850 | 345020 | 329477.01 | Posted | S. Patel
INV-CIV-08-7669 | Aug-24 | Civil | CI-06 | Site Roads & Hardstanding | Judlau Contracting | PO-34957 | 318480 | 300209.1 | Posted | J. Martinez
INV-CIV-09-2588 | Sep-24 | Civil | CI-06 | Site Roads & Hardstanding | Judlau Contracting | PO-96374 | 265400 | 271034.62 | Posted | S. Patel
INV-CIV-10-6804 | Oct-24 | Civil | CI-06 | Site Roads & Hardstanding | Judlau Contracting | PO-65519 | 212320 | 0 | Forecast | S. Patel
INV-CIV-11-8651 | Nov-24 | Civil | CI-06 | Site Roads & Hardstanding | Judlau Contracting | PO-17100 | 159240 | 0 | Forecast | J. Martinez
INV-CIV-12-1993 | Dec-24 | Civil | CI-06 | Site Roads & Hardstanding | Judlau Contracting | PO-62772 | 106160 | 0 | Forecast | R. Okafor
INV-CIV-01-5073 | Jan-24 | Civil | CI-07 | Retaining Walls | Posillico Civil | PO-35112 | 41880 | 48089.61 | Posted | A. Chen
INV-CIV-02-9786 | Feb-24 | Civil | CI-07 | Retaining Walls | Posillico Civil | PO-68800 | 52350 | 56761.78 | Posted | A. Chen
INV-CIV-03-7912 | Mar-24 | Civil | CI-07 | Retaining Walls | Posillico Civil | PO-34050 | 62820 | 68825.73 | Posted | R. Okafor
INV-CIV-04-8579 | Apr-24 | Civil | CI-07 | Retaining Walls | Posillico Civil | PO-42742 | 83760 | 89213.82 | Posted | J. Martinez
INV-CIV-05-8260 | May-24 | Civil | CI-07 | Retaining Walls | Posillico Civil | PO-82132 | 115170 | 124893.94 | Posted | J. Martinez
INV-CIV-06-1828 | Jun-24 | Civil | CI-07 | Retaining Walls | Posillico Civil | PO-95477 | 136110 | 141956.19 | Posted | J. Martinez
INV-CIV-07-2528 | Jul-24 | Civil | CI-07 | Retaining Walls | Posillico Civil | PO-40982 | 136110 | 138882.17 | Posted | A. Chen
INV-CIV-08-7658 | Aug-24 | Civil | CI-07 | Retaining Walls | Posillico Civil | PO-73653 | 125640 | 126129.21 | Posted | S. Patel
INV-CIV-09-4502 | Sep-24 | Civil | CI-07 | Retaining Walls | Posillico Civil | PO-62565 | 104700 | 101900.21 | Posted | J. Martinez
INV-CIV-10-3697 | Oct-24 | Civil | CI-07 | Retaining Walls | Posillico Civil | PO-59672 | 83760 | 0 | Forecast | J. Martinez
INV-CIV-11-7396 | Nov-24 | Civil | CI-07 | Retaining Walls | Posillico Civil | PO-44760 | 62820 | 0 | Forecast | S. Patel
INV-CIV-12-5673 | Dec-24 | Civil | CI-07 | Retaining Walls | Posillico Civil | PO-65444 | 41880 | 0 | Forecast | S. Patel
INV-CIV-01-4111 | Jan-24 | Civil | CI-08 | Drainage & Stormwater | Posillico Civil | PO-48890 | 91440 | 98380.32 | Posted | A. Chen
INV-CIV-02-1958 | Feb-24 | Civil | CI-08 | Drainage & Stormwater | Posillico Civil | PO-85914 | 114300 | 118867.9 | Posted | J. Martinez
INV-CIV-03-6138 | Mar-24 | Civil | CI-08 | Drainage & Stormwater | Posillico Civil | PO-17492 | 137160 | 143746.36 | Posted | J. Martinez
INV-CIV-04-8811 | Apr-24 | Civil | CI-08 | Drainage & Stormwater | Posillico Civil | PO-75909 | 182880 | 208125.43 | Posted | A. Chen
INV-CIV-05-1931 | May-24 | Civil | CI-08 | Drainage & Stormwater | Posillico Civil | PO-76562 | 251460 | 280410.92 | Posted | J. Martinez
INV-CIV-06-4044 | Jun-24 | Civil | CI-08 | Drainage & Stormwater | Posillico Civil | PO-18981 | 297180 | 334806.87 | Posted | J. Martinez
INV-CIV-07-4853 | Jul-24 | Civil | CI-08 | Drainage & Stormwater | Posillico Civil | PO-62923 | 297180 | 291794.99 | Posted | J. Martinez
INV-CIV-08-5033 | Aug-24 | Civil | CI-08 | Drainage & Stormwater | Posillico Civil | PO-85880 | 274320 | 261685.67 | Posted | J. Martinez
INV-CIV-09-2343 | Sep-24 | Civil | CI-08 | Drainage & Stormwater | Posillico Civil | PO-64948 | 228600 | 231140.03 | Posted | R. Okafor
INV-CIV-10-5272 | Oct-24 | Civil | CI-08 | Drainage & Stormwater | Posillico Civil | PO-36772 | 182880 | 0 | Forecast | R. Okafor
INV-CIV-11-4910 | Nov-24 | Civil | CI-08 | Drainage & Stormwater | Posillico Civil | PO-44814 | 137160 | 0 | Forecast | S. Patel
INV-CIV-12-3144 | Dec-24 | Civil | CI-08 | Drainage & Stormwater | Posillico Civil | PO-98039 | 91440 | 0 | Forecast | R. Okafor
INV-CIV-01-6180 | Jan-24 | Civil | CI-09 | Site Hoarding & Fencing | Tully Construction | PO-19508 | 74000 | 85421.04 | Posted | J. Martinez
INV-CIV-02-8508 | Feb-24 | Civil | CI-09 | Site Hoarding & Fencing | Tully Construction | PO-91416 | 92500 | 98650.82 | Posted | J. Martinez
INV-CIV-03-2200 | Mar-24 | Civil | CI-09 | Site Hoarding & Fencing | Tully Construction | PO-80468 | 111000 | 121608.25 | Posted | A. Chen
INV-CIV-04-9288 | Apr-24 | Civil | CI-09 | Site Hoarding & Fencing | Tully Construction | PO-44760 | 148000 | 164547.84 | Posted | A. Chen
INV-CIV-05-6718 | May-24 | Civil | CI-09 | Site Hoarding & Fencing | Tully Construction | PO-19016 | 203500 | 224358.87 | Posted | A. Chen
INV-CIV-06-7054 | Jun-24 | Civil | CI-09 | Site Hoarding & Fencing | Tully Construction | PO-47353 | 240500 | 258959.91 | Posted | A. Chen
INV-CIV-07-8179 | Jul-24 | Civil | CI-09 | Site Hoarding & Fencing | Tully Construction | PO-81200 | 240500 | 225561.92 | Posted | R. Okafor
INV-CIV-08-9666 | Aug-24 | Civil | CI-09 | Site Hoarding & Fencing | Tully Construction | PO-11025 | 222000 | 211517.73 | Posted | R. Okafor
INV-CIV-09-2697 | Sep-24 | Civil | CI-09 | Site Hoarding & Fencing | Tully Construction | PO-27601 | 185000 | 174568.13 | Posted | R. Okafor
INV-CIV-10-2891 | Oct-24 | Civil | CI-09 | Site Hoarding & Fencing | Tully Construction | PO-24029 | 148000 | 0 | Forecast | A. Chen
INV-CIV-11-5462 | Nov-24 | Civil | CI-09 | Site Hoarding & Fencing | Tully Construction | PO-46930 | 111000 | 0 | Forecast | A. Chen
INV-CIV-12-6617 | Dec-24 | Civil | CI-09 | Site Hoarding & Fencing | Tully Construction | PO-36685 | 74000 | 0 | Forecast | R. Okafor
INV-CIV-01-9004 | Jan-24 | Civil | CI-10 | Mobilization | Judlau Contracting | PO-42914 | 8000 | 9122.77 | Posted | J. Martinez
INV-CIV-02-2512 | Feb-24 | Civil | CI-10 | Mobilization | Judlau Contracting | PO-93136 | 10000 | 10403.22 | Posted | S. Patel
INV-CIV-03-5533 | Mar-24 | Civil | CI-10 | Mobilization | Judlau Contracting | PO-15778 | 12000 | 12810.97 | Posted | J. Martinez
INV-CIV-04-6464 | Apr-24 | Civil | CI-10 | Mobilization | Judlau Contracting | PO-27146 | 16000 | 18525.47 | Posted | R. Okafor
INV-CIV-05-3647 | May-24 | Civil | CI-10 | Mobilization | Judlau Contracting | PO-67912 | 22000 | 23593.29 | Posted | S. Patel
INV-CIV-06-1158 | Jun-24 | Civil | CI-10 | Mobilization | Judlau Contracting | PO-24663 | 26000 | 27947.28 | Posted | J. Martinez
INV-CIV-07-3442 | Jul-24 | Civil | CI-10 | Mobilization | Judlau Contracting | PO-81511 | 26000 | 26254.21 | Posted | J. Martinez
INV-CIV-08-7049 | Aug-24 | Civil | CI-10 | Mobilization | Judlau Contracting | PO-86350 | 24000 | 23154.54 | Posted | A. Chen
INV-CIV-09-8041 | Sep-24 | Civil | CI-10 | Mobilization | Judlau Contracting | PO-26704 | 20000 | 18962.42 | Posted | J. Martinez
INV-CIV-10-6050 | Oct-24 | Civil | CI-10 | Mobilization | Judlau Contracting | PO-57795 | 16000 | 0 | Forecast | J. Martinez
INV-CIV-11-6862 | Nov-24 | Civil | CI-10 | Mobilization | Judlau Contracting | PO-37535 | 12000 | 0 | Forecast | A. Chen
INV-CIV-12-2684 | Dec-24 | Civil | CI-10 | Mobilization | Judlau Contracting | PO-56357 | 8000 | 0 | Forecast | S. Patel
INV-STR-01-3532 | Jan-24 | Structural Steel | ST-01 | Steel Fabrication | Schuff Steel | PO-41029 | 32180 | 33825.31 | Posted | A. Chen
INV-STR-02-3900 | Feb-24 | Structural Steel | ST-01 | Steel Fabrication | Schuff Steel | PO-64040 | 48270 | 52658.48 | Posted | J. Martinez
INV-STR-03-3938 | Mar-24 | Structural Steel | ST-01 | Steel Fabrication | Schuff Steel | PO-53540 | 80450 | 87600.08 | Posted | S. Patel
INV-STR-04-5065 | Apr-24 | Structural Steel | ST-01 | Steel Fabrication | Schuff Steel | PO-44970 | 128720 | 136209.6 | Posted | A. Chen
INV-STR-05-2771 | May-24 | Structural Steel | ST-01 | Steel Fabrication | Schuff Steel | PO-60140 | 176990 | 194693.29 | Posted | J. Martinez
INV-STR-06-8711 | Jun-24 | Structural Steel | ST-01 | Steel Fabrication | Schuff Steel | PO-39154 | 225260 | 253719.89 | Posted | A. Chen
INV-STR-07-8541 | Jul-24 | Structural Steel | ST-01 | Steel Fabrication | Schuff Steel | PO-55830 | 241350 | 257630.2 | Posted | R. Okafor
INV-STR-08-4728 | Aug-24 | Structural Steel | ST-01 | Steel Fabrication | Schuff Steel | PO-39219 | 193080 | 224071.25 | Posted | J. Martinez
INV-STR-09-4164 | Sep-24 | Structural Steel | ST-01 | Steel Fabrication | Schuff Steel | PO-62227 | 176990 | 0 | Forecast | R. Okafor
INV-STR-10-5564 | Oct-24 | Structural Steel | ST-01 | Steel Fabrication | Schuff Steel | PO-19099 | 128720 | 0 | Forecast | R. Okafor
INV-STR-11-6753 | Nov-24 | Structural Steel | ST-01 | Steel Fabrication | Schuff Steel | PO-94080 | 96540 | 0 | Forecast | S. Patel
INV-STR-12-9785 | Dec-24 | Structural Steel | ST-01 | Steel Fabrication | Schuff Steel | PO-53404 | 80450 | 0 | Forecast | J. Martinez
INV-STR-01-5279 | Jan-24 | Structural Steel | ST-02 | Steel Erection | Banker Steel | PO-33405 | 42840 | 45895.22 | Posted | R. Okafor
INV-STR-02-1626 | Feb-24 | Structural Steel | ST-02 | Steel Erection | Banker Steel | PO-24208 | 64260 | 69722.05 | Posted | S. Patel
INV-STR-03-6663 | Mar-24 | Structural Steel | ST-02 | Steel Erection | Banker Steel | PO-51114 | 107100 | 125611.12 | Posted | S. Patel
INV-STR-04-9379 | Apr-24 | Structural Steel | ST-02 | Steel Erection | Banker Steel | PO-25157 | 171360 | 197212.95 | Posted | S. Patel
INV-STR-05-4114 | May-24 | Structural Steel | ST-02 | Steel Erection | Banker Steel | PO-43386 | 235620 | 256926.31 | Posted | J. Martinez
INV-STR-06-8144 | Jun-24 | Structural Steel | ST-02 | Steel Erection | Banker Steel | PO-10221 | 299880 | 323353.01 | Posted | A. Chen
INV-STR-07-6967 | Jul-24 | Structural Steel | ST-02 | Steel Erection | Banker Steel | PO-66531 | 321300 | 342193.75 | Posted | J. Martinez
INV-STR-08-6409 | Aug-24 | Structural Steel | ST-02 | Steel Erection | Banker Steel | PO-91678 | 257040 | 291331.88 | Posted | R. Okafor
INV-STR-09-3041 | Sep-24 | Structural Steel | ST-02 | Steel Erection | Banker Steel | PO-49363 | 235620 | 0 | Forecast | R. Okafor
INV-STR-10-7691 | Oct-24 | Structural Steel | ST-02 | Steel Erection | Banker Steel | PO-52753 | 171360 | 0 | Forecast | S. Patel
INV-STR-11-5844 | Nov-24 | Structural Steel | ST-02 | Steel Erection | Banker Steel | PO-82667 | 128520 | 0 | Forecast | A. Chen
INV-STR-12-4143 | Dec-24 | Structural Steel | ST-02 | Steel Erection | Banker Steel | PO-65108 | 107100 | 0 | Forecast | S. Patel
INV-STR-01-3851 | Jan-24 | Structural Steel | ST-03 | Connection Design | Schuff Steel | PO-90676 | 122740 | 122908.54 | Posted | R. Okafor
INV-STR-02-7653 | Feb-24 | Structural Steel | ST-03 | Connection Design | Schuff Steel | PO-81819 | 184110 | 204739.91 | Posted | J. Martinez
INV-STR-03-5978 | Mar-24 | Structural Steel | ST-03 | Connection Design | Schuff Steel | PO-47606 | 306850 | 343764.07 | Posted | A. Chen
INV-STR-04-8043 | Apr-24 | Structural Steel | ST-03 | Connection Design | Schuff Steel | PO-86019 | 490960 | 515833.34 | Posted | R. Okafor
INV-STR-05-8618 | May-24 | Structural Steel | ST-03 | Connection Design | Schuff Steel | PO-67905 | 675070 | 738142.11 | Posted | S. Patel
INV-STR-06-4501 | Jun-24 | Structural Steel | ST-03 | Connection Design | Schuff Steel | PO-77000 | 859180 | 964520.47 | Posted | S. Patel
INV-STR-07-3780 | Jul-24 | Structural Steel | ST-03 | Connection Design | Schuff Steel | PO-96356 | 920550 | 974278.57 | Posted | J. Martinez
INV-STR-08-5649 | Aug-24 | Structural Steel | ST-03 | Connection Design | Schuff Steel | PO-77561 | 736440 | 822751.01 | Posted | R. Okafor
INV-STR-09-2530 | Sep-24 | Structural Steel | ST-03 | Connection Design | Schuff Steel | PO-40784 | 675070 | 0 | Forecast | R. Okafor
INV-STR-10-4680 | Oct-24 | Structural Steel | ST-03 | Connection Design | Schuff Steel | PO-36100 | 490960 | 0 | Forecast | A. Chen
INV-STR-11-1400 | Nov-24 | Structural Steel | ST-03 | Connection Design | Schuff Steel | PO-16057 | 368220 | 0 | Forecast | A. Chen
INV-STR-12-8784 | Dec-24 | Structural Steel | ST-03 | Connection Design | Schuff Steel | PO-90120 | 306850 | 0 | Forecast | J. Martinez
INV-STR-01-7790 | Jan-24 | Structural Steel | ST-04 | Fireproofing Steel | Supreme Steel | PO-92544 | 82940 | 86995.15 | Posted | A. Chen
INV-STR-02-7291 | Feb-24 | Structural Steel | ST-04 | Fireproofing Steel | Supreme Steel | PO-74799 | 124410 | 143497.18 | Posted | S. Patel
INV-STR-03-4997 | Mar-24 | Structural Steel | ST-04 | Fireproofing Steel | Supreme Steel | PO-29342 | 207350 | 226241.7 | Posted | J. Martinez
INV-STR-04-2746 | Apr-24 | Structural Steel | ST-04 | Fireproofing Steel | Supreme Steel | PO-65724 | 331760 | 371217.85 | Posted | A. Chen
INV-STR-05-3881 | May-24 | Structural Steel | ST-04 | Fireproofing Steel | Supreme Steel | PO-77889 | 456170 | 523425.72 | Posted | S. Patel
INV-STR-06-1822 | Jun-24 | Structural Steel | ST-04 | Fireproofing Steel | Supreme Steel | PO-83060 | 580580 | 609767.94 | Posted | A. Chen
INV-STR-07-2988 | Jul-24 | Structural Steel | ST-04 | Fireproofing Steel | Supreme Steel | PO-69829 | 622050 | 691387.54 | Posted | A. Chen
INV-STR-08-8612 | Aug-24 | Structural Steel | ST-04 | Fireproofing Steel | Supreme Steel | PO-97500 | 497640 | 568811.58 | Posted | R. Okafor
INV-STR-09-8251 | Sep-24 | Structural Steel | ST-04 | Fireproofing Steel | Supreme Steel | PO-90301 | 456170 | 0 | Forecast | S. Patel
INV-STR-10-9976 | Oct-24 | Structural Steel | ST-04 | Fireproofing Steel | Supreme Steel | PO-68446 | 331760 | 0 | Forecast | A. Chen
INV-STR-11-8777 | Nov-24 | Structural Steel | ST-04 | Fireproofing Steel | Supreme Steel | PO-68991 | 248820 | 0 | Forecast | R. Okafor
INV-STR-12-5050 | Dec-24 | Structural Steel | ST-04 | Fireproofing Steel | Supreme Steel | PO-93579 | 207350 | 0 | Forecast | R. Okafor
INV-STR-01-8939 | Jan-24 | Structural Steel | ST-05 | Secondary Steelwork | Schuff Steel | PO-92149 | 69960 | 74429.89 | Posted | A. Chen
INV-STR-02-5499 | Feb-24 | Structural Steel | ST-05 | Secondary Steelwork | Schuff Steel | PO-67654 | 104940 | 116975.39 | Posted | J. Martinez
INV-STR-03-5681 | Mar-24 | Structural Steel | ST-05 | Secondary Steelwork | Schuff Steel | PO-40735 | 174900 | 196588.78 | Posted | R. Okafor
INV-STR-04-6502 | Apr-24 | Structural Steel | ST-05 | Secondary Steelwork | Schuff Steel | PO-51904 | 279840 | 295212.14 | Posted | J. Martinez
INV-STR-05-3267 | May-24 | Structural Steel | ST-05 | Secondary Steelwork | Schuff Steel | PO-29769 | 384780 | 444680.52 | Posted | A. Chen
INV-STR-06-7275 | Jun-24 | Structural Steel | ST-05 | Secondary Steelwork | Schuff Steel | PO-30028 | 489720 | 518731.64 | Posted | A. Chen
INV-STR-07-2052 | Jul-24 | Structural Steel | ST-05 | Secondary Steelwork | Schuff Steel | PO-64377 | 524700 | 552300.1 | Posted | S. Patel
INV-STR-08-6421 | Aug-24 | Structural Steel | ST-05 | Secondary Steelwork | Schuff Steel | PO-81121 | 419760 | 463893.48 | Posted | S. Patel
INV-STR-09-7812 | Sep-24 | Structural Steel | ST-05 | Secondary Steelwork | Schuff Steel | PO-18161 | 384780 | 0 | Forecast | A. Chen
INV-STR-10-7883 | Oct-24 | Structural Steel | ST-05 | Secondary Steelwork | Schuff Steel | PO-61049 | 279840 | 0 | Forecast | J. Martinez
INV-STR-11-7232 | Nov-24 | Structural Steel | ST-05 | Secondary Steelwork | Schuff Steel | PO-72518 | 209880 | 0 | Forecast | J. Martinez
INV-STR-12-6763 | Dec-24 | Structural Steel | ST-05 | Secondary Steelwork | Schuff Steel | PO-49139 | 174900 | 0 | Forecast | S. Patel
INV-STR-01-9818 | Jan-24 | Structural Steel | ST-06 | Steel Decking | Supreme Steel | PO-81582 | 126880 | 134434.91 | Posted | A. Chen
INV-STR-02-8999 | Feb-24 | Structural Steel | ST-06 | Steel Decking | Supreme Steel | PO-38760 | 190320 | 213069.35 | Posted | R. Okafor
INV-STR-03-8140 | Mar-24 | Structural Steel | ST-06 | Steel Decking | Supreme Steel | PO-73654 | 317200 | 338090.11 | Posted | J. Martinez
INV-STR-04-7371 | Apr-24 | Structural Steel | ST-06 | Steel Decking | Supreme Steel | PO-54057 | 507520 | 558947.12 | Posted | S. Patel
INV-STR-05-3704 | May-24 | Structural Steel | ST-06 | Steel Decking | Supreme Steel | PO-71261 | 697840 | 758970.14 | Posted | A. Chen
INV-STR-06-9751 | Jun-24 | Structural Steel | ST-06 | Steel Decking | Supreme Steel | PO-13534 | 888160 | 971850.74 | Posted | S. Patel
INV-STR-07-1444 | Jul-24 | Structural Steel | ST-06 | Steel Decking | Supreme Steel | PO-21003 | 951600 | 1000399.14 | Posted | S. Patel
INV-STR-08-3223 | Aug-24 | Structural Steel | ST-06 | Steel Decking | Supreme Steel | PO-70515 | 761280 | 898653.2 | Posted | A. Chen
INV-STR-09-1823 | Sep-24 | Structural Steel | ST-06 | Steel Decking | Supreme Steel | PO-44099 | 697840 | 0 | Forecast | S. Patel
INV-STR-10-6363 | Oct-24 | Structural Steel | ST-06 | Steel Decking | Supreme Steel | PO-37742 | 507520 | 0 | Forecast | S. Patel
INV-STR-11-6355 | Nov-24 | Structural Steel | ST-06 | Steel Decking | Supreme Steel | PO-54236 | 380640 | 0 | Forecast | S. Patel
INV-STR-12-5558 | Dec-24 | Structural Steel | ST-06 | Steel Decking | Supreme Steel | PO-65255 | 317200 | 0 | Forecast | R. Okafor
INV-STR-01-8705 | Jan-24 | Structural Steel | ST-07 | Temporary Works Steel | Banker Steel | PO-12540 | 35640 | 36998.14 | Posted | J. Martinez
INV-STR-02-6733 | Feb-24 | Structural Steel | ST-07 | Temporary Works Steel | Banker Steel | PO-39389 | 53460 | 61374.23 | Posted | J. Martinez
INV-STR-03-1659 | Mar-24 | Structural Steel | ST-07 | Temporary Works Steel | Banker Steel | PO-14067 | 89100 | 96174.75 | Posted | A. Chen
INV-STR-04-4266 | Apr-24 | Structural Steel | ST-07 | Temporary Works Steel | Banker Steel | PO-12671 | 142560 | 154323.67 | Posted | A. Chen
INV-STR-05-4908 | May-24 | Structural Steel | ST-07 | Temporary Works Steel | Banker Steel | PO-26544 | 196020 | 210713.88 | Posted | S. Patel
INV-STR-06-2874 | Jun-24 | Structural Steel | ST-07 | Temporary Works Steel | Banker Steel | PO-83920 | 249480 | 280509.74 | Posted | A. Chen
INV-STR-07-8619 | Jul-24 | Structural Steel | ST-07 | Temporary Works Steel | Banker Steel | PO-43586 | 267300 | 301426.43 | Posted | R. Okafor
INV-STR-08-3749 | Aug-24 | Structural Steel | ST-07 | Temporary Works Steel | Banker Steel | PO-89415 | 213840 | 241702.26 | Posted | J. Martinez
INV-STR-09-3683 | Sep-24 | Structural Steel | ST-07 | Temporary Works Steel | Banker Steel | PO-50768 | 196020 | 0 | Forecast | J. Martinez
INV-STR-10-1420 | Oct-24 | Structural Steel | ST-07 | Temporary Works Steel | Banker Steel | PO-50888 | 142560 | 0 | Forecast | S. Patel
INV-STR-11-7498 | Nov-24 | Structural Steel | ST-07 | Temporary Works Steel | Banker Steel | PO-35995 | 106920 | 0 | Forecast | J. Martinez
INV-STR-12-4978 | Dec-24 | Structural Steel | ST-07 | Temporary Works Steel | Banker Steel | PO-23356 | 89100 | 0 | Forecast | R. Okafor
INV-STR-01-2983 | Jan-24 | Structural Steel | ST-08 | Misc Metalwork | Schuff Steel | PO-84177 | 49820 | 53147.89 | Posted | J. Martinez
INV-STR-02-6688 | Feb-24 | Structural Steel | ST-08 | Misc Metalwork | Schuff Steel | PO-79827 | 74730 | 84810.66 | Posted | S. Patel
INV-STR-03-7071 | Mar-24 | Structural Steel | ST-08 | Misc Metalwork | Schuff Steel | PO-19038 | 124550 | 140266.03 | Posted | R. Okafor
INV-STR-04-1207 | Apr-24 | Structural Steel | ST-08 | Misc Metalwork | Schuff Steel | PO-65057 | 199280 | 219857.96 | Posted | S. Patel
INV-STR-05-2729 | May-24 | Structural Steel | ST-08 | Misc Metalwork | Schuff Steel | PO-66822 | 274010 | 298483.53 | Posted | R. Okafor
INV-STR-06-8532 | Jun-24 | Structural Steel | ST-08 | Misc Metalwork | Schuff Steel | PO-30052 | 348740 | 360835.93 | Posted | S. Patel
INV-STR-07-3885 | Jul-24 | Structural Steel | ST-08 | Misc Metalwork | Schuff Steel | PO-78386 | 373650 | 422161.27 | Posted | R. Okafor
INV-STR-08-9817 | Aug-24 | Structural Steel | ST-08 | Misc Metalwork | Schuff Steel | PO-73372 | 298920 | 360113.44 | Posted | S. Patel
INV-STR-09-8136 | Sep-24 | Structural Steel | ST-08 | Misc Metalwork | Schuff Steel | PO-87656 | 274010 | 0 | Forecast | R. Okafor
INV-STR-10-6280 | Oct-24 | Structural Steel | ST-08 | Misc Metalwork | Schuff Steel | PO-42177 | 199280 | 0 | Forecast | J. Martinez
INV-STR-11-5569 | Nov-24 | Structural Steel | ST-08 | Misc Metalwork | Schuff Steel | PO-69087 | 149460 | 0 | Forecast | A. Chen
INV-STR-12-8613 | Dec-24 | Structural Steel | ST-08 | Misc Metalwork | Schuff Steel | PO-84691 | 124550 | 0 | Forecast | S. Patel
INV-STR-01-1470 | Jan-24 | Structural Steel | ST-09 | NDT Testing | Supreme Steel | PO-74789 | 81020 | 86203.31 | Posted | R. Okafor
INV-STR-02-3979 | Feb-24 | Structural Steel | ST-09 | NDT Testing | Supreme Steel | PO-73904 | 121530 | 131531.1 | Posted | A. Chen
INV-STR-03-6813 | Mar-24 | Structural Steel | ST-09 | NDT Testing | Supreme Steel | PO-43862 | 202550 | 223435.23 | Posted | R. Okafor
INV-STR-04-5581 | Apr-24 | Structural Steel | ST-09 | NDT Testing | Supreme Steel | PO-88139 | 324080 | 364543.05 | Posted | R. Okafor
INV-STR-05-1166 | May-24 | Structural Steel | ST-09 | NDT Testing | Supreme Steel | PO-77715 | 445610 | 518059.93 | Posted | A. Chen
INV-STR-06-2402 | Jun-24 | Structural Steel | ST-09 | NDT Testing | Supreme Steel | PO-41635 | 567140 | 635379.12 | Posted | S. Patel
INV-STR-07-9004 | Jul-24 | Structural Steel | ST-09 | NDT Testing | Supreme Steel | PO-82768 | 607650 | 678793.55 | Posted | A. Chen
INV-STR-08-8800 | Aug-24 | Structural Steel | ST-09 | NDT Testing | Supreme Steel | PO-94659 | 486120 | 571086.65 | Posted | S. Patel
INV-STR-09-8342 | Sep-24 | Structural Steel | ST-09 | NDT Testing | Supreme Steel | PO-12260 | 445610 | 0 | Forecast | J. Martinez
INV-STR-10-5820 | Oct-24 | Structural Steel | ST-09 | NDT Testing | Supreme Steel | PO-39045 | 324080 | 0 | Forecast | S. Patel
INV-STR-11-4986 | Nov-24 | Structural Steel | ST-09 | NDT Testing | Supreme Steel | PO-50135 | 243060 | 0 | Forecast | R. Okafor
INV-STR-12-8753 | Dec-24 | Structural Steel | ST-09 | NDT Testing | Supreme Steel | PO-82544 | 202550 | 0 | Forecast | R. Okafor
INV-MEP-01-6419 | Jan-24 | MEP | ME-01 | Mechanical HVAC | Petrocelli Electric | PO-56112 | 36430 | 35497.35 | Posted | S. Patel
INV-MEP-02-5438 | Feb-24 | MEP | ME-01 | Mechanical HVAC | Petrocelli Electric | PO-50189 | 72860 | 83936.99 | Posted | R. Okafor
INV-MEP-03-4777 | Mar-24 | MEP | ME-01 | Mechanical HVAC | Petrocelli Electric | PO-25814 | 145720 | 165786.55 | Posted | A. Chen
INV-MEP-04-6169 | Apr-24 | MEP | ME-01 | Mechanical HVAC | Petrocelli Electric | PO-25670 | 218580 | 253650.11 | Posted | A. Chen
INV-MEP-05-4138 | May-24 | MEP | ME-01 | Mechanical HVAC | Petrocelli Electric | PO-38361 | 327870 | 380149.7 | Posted | S. Patel
INV-MEP-06-5530 | Jun-24 | MEP | ME-01 | Mechanical HVAC | Petrocelli Electric | PO-87278 | 437160 | 502553.57 | Posted | R. Okafor
INV-MEP-07-2647 | Jul-24 | MEP | ME-01 | Mechanical HVAC | Petrocelli Electric | PO-35443 | 510020 | 575745.79 | Posted | R. Okafor
INV-MEP-08-4727 | Aug-24 | MEP | ME-01 | Mechanical HVAC | Petrocelli Electric | PO-57301 | 510020 | 0 | Forecast | A. Chen
INV-MEP-09-5952 | Sep-24 | MEP | ME-01 | Mechanical HVAC | Petrocelli Electric | PO-11854 | 473590 | 0 | Forecast | A. Chen
INV-MEP-10-5494 | Oct-24 | MEP | ME-01 | Mechanical HVAC | Petrocelli Electric | PO-15965 | 364300 | 0 | Forecast | J. Martinez
INV-MEP-11-5786 | Nov-24 | MEP | ME-01 | Mechanical HVAC | Petrocelli Electric | PO-26551 | 291440 | 0 | Forecast | S. Patel
INV-MEP-12-2680 | Dec-24 | MEP | ME-01 | Mechanical HVAC | Petrocelli Electric | PO-11607 | 255010 | 0 | Forecast | R. Okafor
INV-MEP-01-8843 | Jan-24 | MEP | ME-02 | Plumbing & Drainage | Petrocelli Electric | PO-67733 | 37280 | 37566.7 | Posted | R. Okafor
INV-MEP-02-4020 | Feb-24 | MEP | ME-02 | Plumbing & Drainage | Petrocelli Electric | PO-16734 | 74560 | 81954.63 | Posted | R. Okafor
INV-MEP-03-8827 | Mar-24 | MEP | ME-02 | Plumbing & Drainage | Petrocelli Electric | PO-24953 | 149120 | 166261.78 | Posted | J. Martinez
INV-MEP-04-7565 | Apr-24 | MEP | ME-02 | Plumbing & Drainage | Petrocelli Electric | PO-74454 | 223680 | 255332.32 | Posted | J. Martinez
INV-MEP-05-1878 | May-24 | MEP | ME-02 | Plumbing & Drainage | Petrocelli Electric | PO-29887 | 335520 | 375566.01 | Posted | A. Chen
INV-MEP-06-5978 | Jun-24 | MEP | ME-02 | Plumbing & Drainage | Petrocelli Electric | PO-21164 | 447360 | 475789.11 | Posted | A. Chen
INV-MEP-07-2940 | Jul-24 | MEP | ME-02 | Plumbing & Drainage | Petrocelli Electric | PO-83147 | 521920 | 597592.67 | Posted | S. Patel
INV-MEP-08-4697 | Aug-24 | MEP | ME-02 | Plumbing & Drainage | Petrocelli Electric | PO-78494 | 521920 | 0 | Forecast | S. Patel
INV-MEP-09-8381 | Sep-24 | MEP | ME-02 | Plumbing & Drainage | Petrocelli Electric | PO-68028 | 484640 | 0 | Forecast | R. Okafor
INV-MEP-10-8025 | Oct-24 | MEP | ME-02 | Plumbing & Drainage | Petrocelli Electric | PO-50026 | 372800 | 0 | Forecast | J. Martinez
INV-MEP-11-2625 | Nov-24 | MEP | ME-02 | Plumbing & Drainage | Petrocelli Electric | PO-37235 | 298240 | 0 | Forecast | A. Chen
INV-MEP-12-5335 | Dec-24 | MEP | ME-02 | Plumbing & Drainage | Petrocelli Electric | PO-96563 | 260960 | 0 | Forecast | J. Martinez
INV-MEP-01-4929 | Jan-24 | MEP | ME-03 | Electrical HV | Forest Electric | PO-32782 | 16250 | 15725.3 | Posted | J. Martinez
INV-MEP-02-3564 | Feb-24 | MEP | ME-03 | Electrical HV | Forest Electric | PO-10350 | 32500 | 37324.64 | Posted | S. Patel
INV-MEP-03-8381 | Mar-24 | MEP | ME-03 | Electrical HV | Forest Electric | PO-87832 | 65000 | 78143.12 | Posted | S. Patel
INV-MEP-04-5771 | Apr-24 | MEP | ME-03 | Electrical HV | Forest Electric | PO-14278 | 97500 | 113391.84 | Posted | A. Chen
INV-MEP-05-5720 | May-24 | MEP | ME-03 | Electrical HV | Forest Electric | PO-47056 | 146250 | 165201.78 | Posted | S. Patel
INV-MEP-06-2166 | Jun-24 | MEP | ME-03 | Electrical HV | Forest Electric | PO-40595 | 195000 | 207199.07 | Posted | R. Okafor
INV-MEP-07-4241 | Jul-24 | MEP | ME-03 | Electrical HV | Forest Electric | PO-65723 | 227500 | 267747.08 | Posted | J. Martinez
INV-MEP-08-9922 | Aug-24 | MEP | ME-03 | Electrical HV | Forest Electric | PO-39466 | 227500 | 0 | Forecast | A. Chen
INV-MEP-09-5352 | Sep-24 | MEP | ME-03 | Electrical HV | Forest Electric | PO-28643 | 211250 | 0 | Forecast | J. Martinez
INV-MEP-10-1977 | Oct-24 | MEP | ME-03 | Electrical HV | Forest Electric | PO-31747 | 162500 | 0 | Forecast | R. Okafor
INV-MEP-11-5728 | Nov-24 | MEP | ME-03 | Electrical HV | Forest Electric | PO-67560 | 130000 | 0 | Forecast | J. Martinez
INV-MEP-12-8679 | Dec-24 | MEP | ME-03 | Electrical HV | Forest Electric | PO-49857 | 113750 | 0 | Forecast | S. Patel
INV-MEP-01-9199 | Jan-24 | MEP | ME-04 | Electrical LV | Petrocelli Electric | PO-80776 | 97440 | 96740.23 | Posted | S. Patel
INV-MEP-02-8172 | Feb-24 | MEP | ME-04 | Electrical LV | Petrocelli Electric | PO-20543 | 194880 | 224371.59 | Posted | J. Martinez
INV-MEP-03-8078 | Mar-24 | MEP | ME-04 | Electrical LV | Petrocelli Electric | PO-52247 | 389760 | 469004.56 | Posted | R. Okafor
INV-MEP-04-1423 | Apr-24 | MEP | ME-04 | Electrical LV | Petrocelli Electric | PO-21970 | 584640 | 675894.15 | Posted | A. Chen
INV-MEP-05-1339 | May-24 | MEP | ME-04 | Electrical LV | Petrocelli Electric | PO-98117 | 876960 | 983002.23 | Posted | R. Okafor
INV-MEP-06-1659 | Jun-24 | MEP | ME-04 | Electrical LV | Petrocelli Electric | PO-32962 | 1169280 | 1290693.26 | Posted | S. Patel
INV-MEP-07-9502 | Jul-24 | MEP | ME-04 | Electrical LV | Petrocelli Electric | PO-95394 | 1364160 | 1593611.32 | Posted | S. Patel
INV-MEP-08-5557 | Aug-24 | MEP | ME-04 | Electrical LV | Petrocelli Electric | PO-33788 | 1364160 | 0 | Forecast | S. Patel
INV-MEP-09-9056 | Sep-24 | MEP | ME-04 | Electrical LV | Petrocelli Electric | PO-21959 | 1266720 | 0 | Forecast | S. Patel
INV-MEP-10-6700 | Oct-24 | MEP | ME-04 | Electrical LV | Petrocelli Electric | PO-63523 | 974400 | 0 | Forecast | R. Okafor
INV-MEP-11-6260 | Nov-24 | MEP | ME-04 | Electrical LV | Petrocelli Electric | PO-97835 | 779520 | 0 | Forecast | J. Martinez
INV-MEP-12-3634 | Dec-24 | MEP | ME-04 | Electrical LV | Petrocelli Electric | PO-53228 | 682080 | 0 | Forecast | S. Patel
INV-MEP-01-9117 | Jan-24 | MEP | ME-05 | Fire Protection Systems | Arden Building Products | PO-47777 | 42350 | 41574.66 | Posted | S. Patel
INV-MEP-02-1601 | Feb-24 | MEP | ME-05 | Fire Protection Systems | Arden Building Products | PO-69614 | 84700 | 90090.66 | Posted | J. Martinez
INV-MEP-03-6153 | Mar-24 | MEP | ME-05 | Fire Protection Systems | Arden Building Products | PO-43082 | 169400 | 195916.55 | Posted | R. Okafor
INV-MEP-04-2899 | Apr-24 | MEP | ME-05 | Fire Protection Systems | Arden Building Products | PO-62976 | 254100 | 296120.67 | Posted | J. Martinez
INV-MEP-05-9889 | May-24 | MEP | ME-05 | Fire Protection Systems | Arden Building Products | PO-70552 | 381150 | 444755.92 | Posted | S. Patel
INV-MEP-06-1888 | Jun-24 | MEP | ME-05 | Fire Protection Systems | Arden Building Products | PO-34586 | 508200 | 571465.9 | Posted | R. Okafor
INV-MEP-07-9167 | Jul-24 | MEP | ME-05 | Fire Protection Systems | Arden Building Products | PO-91973 | 592900 | 642175.87 | Posted | S. Patel
INV-MEP-08-1845 | Aug-24 | MEP | ME-05 | Fire Protection Systems | Arden Building Products | PO-36680 | 592900 | 0 | Forecast | R. Okafor
INV-MEP-09-9998 | Sep-24 | MEP | ME-05 | Fire Protection Systems | Arden Building Products | PO-27172 | 550550 | 0 | Forecast | R. Okafor
INV-MEP-10-8178 | Oct-24 | MEP | ME-05 | Fire Protection Systems | Arden Building Products | PO-73532 | 423500 | 0 | Forecast | J. Martinez
INV-MEP-11-1472 | Nov-24 | MEP | ME-05 | Fire Protection Systems | Arden Building Products | PO-92578 | 338800 | 0 | Forecast | A. Chen
INV-MEP-12-3594 | Dec-24 | MEP | ME-05 | Fire Protection Systems | Arden Building Products | PO-50730 | 296450 | 0 | Forecast | J. Martinez
INV-MEP-01-7684 | Jan-24 | MEP | ME-06 | BMS Controls | Arden Building Products | PO-22217 | 12550 | 12694.33 | Posted | A. Chen
INV-MEP-02-2858 | Feb-24 | MEP | ME-06 | BMS Controls | Arden Building Products | PO-70482 | 25100 | 28963.04 | Posted | J. Martinez
INV-MEP-03-3522 | Mar-24 | MEP | ME-06 | BMS Controls | Arden Building Products | PO-75323 | 50200 | 55652.21 | Posted | R. Okafor
INV-MEP-04-9337 | Apr-24 | MEP | ME-06 | BMS Controls | Arden Building Products | PO-45838 | 75300 | 84239.12 | Posted | S. Patel
INV-MEP-05-8905 | May-24 | MEP | ME-06 | BMS Controls | Arden Building Products | PO-71894 | 112950 | 134143.11 | Posted | A. Chen
INV-MEP-06-8483 | Jun-24 | MEP | ME-06 | BMS Controls | Arden Building Products | PO-82255 | 150600 | 172219.01 | Posted | A. Chen
INV-MEP-07-7284 | Jul-24 | MEP | ME-06 | BMS Controls | Arden Building Products | PO-34983 | 175700 | 202196.63 | Posted | A. Chen
INV-MEP-08-2143 | Aug-24 | MEP | ME-06 | BMS Controls | Arden Building Products | PO-46208 | 175700 | 0 | Forecast | S. Patel
INV-MEP-09-6568 | Sep-24 | MEP | ME-06 | BMS Controls | Arden Building Products | PO-76550 | 163150 | 0 | Forecast | R. Okafor
INV-MEP-10-1042 | Oct-24 | MEP | ME-06 | BMS Controls | Arden Building Products | PO-47072 | 125500 | 0 | Forecast | R. Okafor
INV-MEP-11-9022 | Nov-24 | MEP | ME-06 | BMS Controls | Arden Building Products | PO-29476 | 100400 | 0 | Forecast | S. Patel
INV-MEP-12-9824 | Dec-24 | MEP | ME-06 | BMS Controls | Arden Building Products | PO-73483 | 87850 | 0 | Forecast | R. Okafor
INV-MEP-01-9903 | Jan-24 | MEP | ME-07 | Lifts & Escalators | Petrocelli Electric | PO-59441 | 52180 | 53236.56 | Posted | S. Patel
INV-MEP-02-6272 | Feb-24 | MEP | ME-07 | Lifts & Escalators | Petrocelli Electric | PO-34727 | 104360 | 113183.01 | Posted | A. Chen
INV-MEP-03-7274 | Mar-24 | MEP | ME-07 | Lifts & Escalators | Petrocelli Electric | PO-40613 | 208720 | 235073.63 | Posted | S. Patel
INV-MEP-04-1715 | Apr-24 | MEP | ME-07 | Lifts & Escalators | Petrocelli Electric | PO-51704 | 313080 | 360421.45 | Posted | S. Patel
INV-MEP-05-7246 | May-24 | MEP | ME-07 | Lifts & Escalators | Petrocelli Electric | PO-60604 | 469620 | 554121.17 | Posted | A. Chen
INV-MEP-06-9115 | Jun-24 | MEP | ME-07 | Lifts & Escalators | Petrocelli Electric | PO-14852 | 626160 | 724878.14 | Posted | A. Chen
INV-MEP-07-9229 | Jul-24 | MEP | ME-07 | Lifts & Escalators | Petrocelli Electric | PO-87356 | 730520 | 858513.37 | Posted | R. Okafor
INV-MEP-08-2644 | Aug-24 | MEP | ME-07 | Lifts & Escalators | Petrocelli Electric | PO-67711 | 730520 | 0 | Forecast | J. Martinez
INV-MEP-09-9617 | Sep-24 | MEP | ME-07 | Lifts & Escalators | Petrocelli Electric | PO-69890 | 678340 | 0 | Forecast | J. Martinez
INV-MEP-10-3361 | Oct-24 | MEP | ME-07 | Lifts & Escalators | Petrocelli Electric | PO-63736 | 521800 | 0 | Forecast | A. Chen
INV-MEP-11-2225 | Nov-24 | MEP | ME-07 | Lifts & Escalators | Petrocelli Electric | PO-71537 | 417440 | 0 | Forecast | R. Okafor
INV-MEP-12-6546 | Dec-24 | MEP | ME-07 | Lifts & Escalators | Petrocelli Electric | PO-91691 | 365260 | 0 | Forecast | S. Patel
INV-MEP-01-2315 | Jan-24 | MEP | ME-08 | Generator Sets | Arden Building Products | PO-53065 | 58330 | 58396.16 | Posted | S. Patel
INV-MEP-02-6188 | Feb-24 | MEP | ME-08 | Generator Sets | Arden Building Products | PO-92155 | 116660 | 128345.46 | Posted | S. Patel
INV-MEP-03-9864 | Mar-24 | MEP | ME-08 | Generator Sets | Arden Building Products | PO-14705 | 233320 | 276321.8 | Posted | J. Martinez
INV-MEP-04-4846 | Apr-24 | MEP | ME-08 | Generator Sets | Arden Building Products | PO-92727 | 349980 | 396671.76 | Posted | R. Okafor
INV-MEP-05-4727 | May-24 | MEP | ME-08 | Generator Sets | Arden Building Products | PO-21846 | 524970 | 612933.15 | Posted | S. Patel
INV-MEP-06-2612 | Jun-24 | MEP | ME-08 | Generator Sets | Arden Building Products | PO-93066 | 699960 | 804741.81 | Posted | J. Martinez
INV-MEP-07-8269 | Jul-24 | MEP | ME-08 | Generator Sets | Arden Building Products | PO-31805 | 816620 | 957557.44 | Posted | R. Okafor
INV-MEP-08-1474 | Aug-24 | MEP | ME-08 | Generator Sets | Arden Building Products | PO-16028 | 816620 | 0 | Forecast | R. Okafor
INV-MEP-09-1919 | Sep-24 | MEP | ME-08 | Generator Sets | Arden Building Products | PO-48452 | 758290 | 0 | Forecast | R. Okafor
INV-MEP-10-7141 | Oct-24 | MEP | ME-08 | Generator Sets | Arden Building Products | PO-66450 | 583300 | 0 | Forecast | A. Chen
INV-MEP-11-5000 | Nov-24 | MEP | ME-08 | Generator Sets | Arden Building Products | PO-79621 | 466640 | 0 | Forecast | S. Patel
INV-MEP-12-3950 | Dec-24 | MEP | ME-08 | Generator Sets | Arden Building Products | PO-32280 | 408310 | 0 | Forecast | A. Chen
INV-MEP-01-7267 | Jan-24 | MEP | ME-09 | Specialist Systems | Forest Electric | PO-91226 | 40590 | 39932.42 | Posted | A. Chen
INV-MEP-02-9153 | Feb-24 | MEP | ME-09 | Specialist Systems | Forest Electric | PO-86435 | 81180 | 88186.98 | Posted | A. Chen
INV-MEP-03-4804 | Mar-24 | MEP | ME-09 | Specialist Systems | Forest Electric | PO-70443 | 162360 | 179133.07 | Posted | R. Okafor
INV-MEP-04-8529 | Apr-24 | MEP | ME-09 | Specialist Systems | Forest Electric | PO-43466 | 243540 | 274081.85 | Posted | J. Martinez
INV-MEP-05-8622 | May-24 | MEP | ME-09 | Specialist Systems | Forest Electric | PO-47700 | 365310 | 398675.81 | Posted | A. Chen
INV-MEP-06-2210 | Jun-24 | MEP | ME-09 | Specialist Systems | Forest Electric | PO-67898 | 487080 | 542034.86 | Posted | R. Okafor
INV-MEP-07-5901 | Jul-24 | MEP | ME-09 | Specialist Systems | Forest Electric | PO-93746 | 568260 | 644056.89 | Posted | S. Patel
INV-MEP-08-5097 | Aug-24 | MEP | ME-09 | Specialist Systems | Forest Electric | PO-69878 | 568260 | 0 | Forecast | R. Okafor
INV-MEP-09-4263 | Sep-24 | MEP | ME-09 | Specialist Systems | Forest Electric | PO-60422 | 527670 | 0 | Forecast | S. Patel
INV-MEP-10-2747 | Oct-24 | MEP | ME-09 | Specialist Systems | Forest Electric | PO-41091 | 405900 | 0 | Forecast | S. Patel
INV-MEP-11-6881 | Nov-24 | MEP | ME-09 | Specialist Systems | Forest Electric | PO-85341 | 324720 | 0 | Forecast | R. Okafor
INV-MEP-12-5837 | Dec-24 | MEP | ME-09 | Specialist Systems | Forest Electric | PO-12875 | 284130 | 0 | Forecast | S. Patel
INV-MEP-01-1132 | Jan-24 | MEP | ME-10 | Testing & Commissioning MEP | Petrocelli Electric | PO-84177 | 24610 | 24084.68 | Posted | J. Martinez
INV-MEP-02-9138 | Feb-24 | MEP | ME-10 | Testing & Commissioning MEP | Petrocelli Electric | PO-47512 | 49220 | 54633.79 | Posted | A. Chen
INV-MEP-03-6772 | Mar-24 | MEP | ME-10 | Testing & Commissioning MEP | Petrocelli Electric | PO-38705 | 98440 | 107890.98 | Posted | A. Chen
INV-MEP-04-5106 | Apr-24 | MEP | ME-10 | Testing & Commissioning MEP | Petrocelli Electric | PO-98835 | 147660 | 157258.47 | Posted | A. Chen
INV-MEP-05-2591 | May-24 | MEP | ME-10 | Testing & Commissioning MEP | Petrocelli Electric | PO-92242 | 221490 | 261660.38 | Posted | J. Martinez
INV-MEP-06-6061 | Jun-24 | MEP | ME-10 | Testing & Commissioning MEP | Petrocelli Electric | PO-67779 | 295320 | 325163.45 | Posted | J. Martinez
INV-MEP-07-6977 | Jul-24 | MEP | ME-10 | Testing & Commissioning MEP | Petrocelli Electric | PO-27224 | 344540 | 374336.7 | Posted | J. Martinez
INV-MEP-08-5835 | Aug-24 | MEP | ME-10 | Testing & Commissioning MEP | Petrocelli Electric | PO-52823 | 344540 | 0 | Forecast | S. Patel
INV-MEP-09-3877 | Sep-24 | MEP | ME-10 | Testing & Commissioning MEP | Petrocelli Electric | PO-36318 | 319930 | 0 | Forecast | A. Chen
INV-MEP-10-9837 | Oct-24 | MEP | ME-10 | Testing & Commissioning MEP | Petrocelli Electric | PO-57953 | 246100 | 0 | Forecast | R. Okafor
INV-MEP-11-3695 | Nov-24 | MEP | ME-10 | Testing & Commissioning MEP | Petrocelli Electric | PO-43681 | 196880 | 0 | Forecast | S. Patel
INV-MEP-12-5835 | Dec-24 | MEP | ME-10 | Testing & Commissioning MEP | Petrocelli Electric | PO-54396 | 172270 | 0 | Forecast | J. Martinez
INV-CON-01-2233 | Jan-24 | Concrete | CO-01 | Rebar Supply | Navillus Contracting | PO-28449 | 50760 | 52465.44 | Posted | A. Chen
INV-CON-02-7511 | Feb-24 | Concrete | CO-01 | Rebar Supply | Navillus Contracting | PO-83048 | 84600 | 84532.78 | Posted | R. Okafor
INV-CON-03-2479 | Mar-24 | Concrete | CO-01 | Rebar Supply | Navillus Contracting | PO-61717 | 101520 | 98919.1 | Posted | J. Martinez
INV-CON-04-5332 | Apr-24 | Concrete | CO-01 | Rebar Supply | Navillus Contracting | PO-80329 | 135360 | 126027.55 | Posted | J. Martinez
INV-CON-05-8451 | May-24 | Concrete | CO-01 | Rebar Supply | Navillus Contracting | PO-58311 | 186120 | 169922.39 | Posted | R. Okafor
INV-CON-06-7242 | Jun-24 | Concrete | CO-01 | Rebar Supply | Navillus Contracting | PO-93695 | 219960 | 211166.86 | Posted | R. Okafor
INV-CON-07-2775 | Jul-24 | Concrete | CO-01 | Rebar Supply | Navillus Contracting | PO-98452 | 219960 | 212541.14 | Posted | A. Chen
INV-CON-08-8724 | Aug-24 | Concrete | CO-01 | Rebar Supply | Navillus Contracting | PO-13280 | 203040 | 217767.01 | Posted | R. Okafor
INV-CON-09-4626 | Sep-24 | Concrete | CO-01 | Rebar Supply | Navillus Contracting | PO-94889 | 186120 | 183944.28 | Posted | J. Martinez
INV-CON-10-8606 | Oct-24 | Concrete | CO-01 | Rebar Supply | Navillus Contracting | PO-49608 | 135360 | 0 | Forecast | S. Patel
INV-CON-11-2911 | Nov-24 | Concrete | CO-01 | Rebar Supply | Navillus Contracting | PO-28320 | 101520 | 0 | Forecast | J. Martinez
INV-CON-12-1609 | Dec-24 | Concrete | CO-01 | Rebar Supply | Navillus Contracting | PO-49893 | 67680 | 0 | Forecast | S. Patel
INV-CON-01-2592 | Jan-24 | Concrete | CO-02 | Rebar Fix | Turner Specialty | PO-40775 | 52680 | 51520.69 | Posted | A. Chen
INV-CON-02-7367 | Feb-24 | Concrete | CO-02 | Rebar Fix | Turner Specialty | PO-69459 | 87800 | 89957.84 | Posted | R. Okafor
INV-CON-03-9850 | Mar-24 | Concrete | CO-02 | Rebar Fix | Turner Specialty | PO-64935 | 105360 | 106068.71 | Posted | A. Chen
INV-CON-04-7797 | Apr-24 | Concrete | CO-02 | Rebar Fix | Turner Specialty | PO-95841 | 140480 | 135946.93 | Posted | J. Martinez
INV-CON-05-9017 | May-24 | Concrete | CO-02 | Rebar Fix | Turner Specialty | PO-90694 | 193160 | 184664.29 | Posted | S. Patel
INV-CON-06-5583 | Jun-24 | Concrete | CO-02 | Rebar Fix | Turner Specialty | PO-14288 | 228280 | 222960.87 | Posted | R. Okafor
INV-CON-07-4559 | Jul-24 | Concrete | CO-02 | Rebar Fix | Turner Specialty | PO-68115 | 228280 | 213962.7 | Posted | S. Patel
INV-CON-08-4868 | Aug-24 | Concrete | CO-02 | Rebar Fix | Turner Specialty | PO-57537 | 210720 | 218069.31 | Posted | J. Martinez
INV-CON-09-7018 | Sep-24 | Concrete | CO-02 | Rebar Fix | Turner Specialty | PO-81364 | 193160 | 192736.72 | Posted | R. Okafor
INV-CON-10-1992 | Oct-24 | Concrete | CO-02 | Rebar Fix | Turner Specialty | PO-62184 | 140480 | 0 | Forecast | R. Okafor
INV-CON-11-4109 | Nov-24 | Concrete | CO-02 | Rebar Fix | Turner Specialty | PO-26011 | 105360 | 0 | Forecast | S. Patel
INV-CON-12-2501 | Dec-24 | Concrete | CO-02 | Rebar Fix | Turner Specialty | PO-96870 | 70240 | 0 | Forecast | A. Chen
INV-CON-01-1349 | Jan-24 | Concrete | CO-03 | Formwork | Plaza Construction | PO-16629 | 157830 | 150165.67 | Posted | R. Okafor
INV-CON-02-4990 | Feb-24 | Concrete | CO-03 | Formwork | Plaza Construction | PO-26505 | 263050 | 247891.77 | Posted | A. Chen
INV-CON-03-2124 | Mar-24 | Concrete | CO-03 | Formwork | Plaza Construction | PO-82641 | 315660 | 296306.97 | Posted | A. Chen
INV-CON-04-4538 | Apr-24 | Concrete | CO-03 | Formwork | Plaza Construction | PO-40539 | 420880 | 386492.06 | Posted | R. Okafor
INV-CON-05-3417 | May-24 | Concrete | CO-03 | Formwork | Plaza Construction | PO-88116 | 578710 | 566592.81 | Posted | J. Martinez
INV-CON-06-5542 | Jun-24 | Concrete | CO-03 | Formwork | Plaza Construction | PO-28964 | 683930 | 687122.48 | Posted | A. Chen
INV-CON-07-9850 | Jul-24 | Concrete | CO-03 | Formwork | Plaza Construction | PO-42853 | 683930 | 655926.61 | Posted | A. Chen
INV-CON-08-2801 | Aug-24 | Concrete | CO-03 | Formwork | Plaza Construction | PO-96646 | 631320 | 636226.99 | Posted | J. Martinez
INV-CON-09-3159 | Sep-24 | Concrete | CO-03 | Formwork | Plaza Construction | PO-11947 | 578710 | 562455.03 | Posted | R. Okafor
INV-CON-10-4898 | Oct-24 | Concrete | CO-03 | Formwork | Plaza Construction | PO-87182 | 420880 | 0 | Forecast | R. Okafor
INV-CON-11-1258 | Nov-24 | Concrete | CO-03 | Formwork | Plaza Construction | PO-32838 | 315660 | 0 | Forecast | R. Okafor
INV-CON-12-1858 | Dec-24 | Concrete | CO-03 | Formwork | Plaza Construction | PO-26614 | 210440 | 0 | Forecast | S. Patel
INV-CON-01-2862 | Jan-24 | Concrete | CO-04 | Ready-Mix Concrete | Plaza Construction | PO-18330 | 100650 | 100382.99 | Posted | S. Patel
INV-CON-02-8344 | Feb-24 | Concrete | CO-04 | Ready-Mix Concrete | Plaza Construction | PO-57453 | 167750 | 159022.6 | Posted | J. Martinez
INV-CON-03-8405 | Mar-24 | Concrete | CO-04 | Ready-Mix Concrete | Plaza Construction | PO-76039 | 201300 | 196635.63 | Posted | A. Chen
INV-CON-04-1710 | Apr-24 | Concrete | CO-04 | Ready-Mix Concrete | Plaza Construction | PO-96363 | 268400 | 255713.02 | Posted | R. Okafor
INV-CON-05-8504 | May-24 | Concrete | CO-04 | Ready-Mix Concrete | Plaza Construction | PO-94323 | 369050 | 352962.24 | Posted | J. Martinez
INV-CON-06-1996 | Jun-24 | Concrete | CO-04 | Ready-Mix Concrete | Plaza Construction | PO-72781 | 436150 | 435241.46 | Posted | S. Patel
INV-CON-07-7984 | Jul-24 | Concrete | CO-04 | Ready-Mix Concrete | Plaza Construction | PO-99928 | 436150 | 400306.19 | Posted | J. Martinez
INV-CON-08-9032 | Aug-24 | Concrete | CO-04 | Ready-Mix Concrete | Plaza Construction | PO-68138 | 402600 | 417429.5 | Posted | J. Martinez
INV-CON-09-2323 | Sep-24 | Concrete | CO-04 | Ready-Mix Concrete | Plaza Construction | PO-52219 | 369050 | 363503.18 | Posted | A. Chen
INV-CON-10-2076 | Oct-24 | Concrete | CO-04 | Ready-Mix Concrete | Plaza Construction | PO-26540 | 268400 | 0 | Forecast | R. Okafor
INV-CON-11-9984 | Nov-24 | Concrete | CO-04 | Ready-Mix Concrete | Plaza Construction | PO-52622 | 201300 | 0 | Forecast | S. Patel
INV-CON-12-9692 | Dec-24 | Concrete | CO-04 | Ready-Mix Concrete | Plaza Construction | PO-48652 | 134200 | 0 | Forecast | S. Patel
INV-CON-01-8048 | Jan-24 | Concrete | CO-05 | Post-Tension Works | Plaza Construction | PO-22999 | 55920 | 55937.54 | Posted | J. Martinez
INV-CON-02-4522 | Feb-24 | Concrete | CO-05 | Post-Tension Works | Plaza Construction | PO-66370 | 93200 | 94592.04 | Posted | S. Patel
INV-CON-03-4743 | Mar-24 | Concrete | CO-05 | Post-Tension Works | Plaza Construction | PO-64239 | 111840 | 111721.25 | Posted | R. Okafor
INV-CON-04-8430 | Apr-24 | Concrete | CO-05 | Post-Tension Works | Plaza Construction | PO-62262 | 149120 | 138690.17 | Posted | S. Patel
INV-CON-05-2557 | May-24 | Concrete | CO-05 | Post-Tension Works | Plaza Construction | PO-50966 | 205040 | 185531.22 | Posted | S. Patel
INV-CON-06-6120 | Jun-24 | Concrete | CO-05 | Post-Tension Works | Plaza Construction | PO-97177 | 242320 | 241990.01 | Posted | R. Okafor
INV-CON-07-7132 | Jul-24 | Concrete | CO-05 | Post-Tension Works | Plaza Construction | PO-30006 | 242320 | 221967.71 | Posted | S. Patel
INV-CON-08-2099 | Aug-24 | Concrete | CO-05 | Post-Tension Works | Plaza Construction | PO-21957 | 223680 | 236878.56 | Posted | J. Martinez
INV-CON-09-2527 | Sep-24 | Concrete | CO-05 | Post-Tension Works | Plaza Construction | PO-66606 | 205040 | 208228.3 | Posted | J. Martinez
INV-CON-10-7105 | Oct-24 | Concrete | CO-05 | Post-Tension Works | Plaza Construction | PO-27054 | 149120 | 0 | Forecast | J. Martinez
INV-CON-11-6400 | Nov-24 | Concrete | CO-05 | Post-Tension Works | Plaza Construction | PO-97819 | 111840 | 0 | Forecast | J. Martinez
INV-CON-12-7730 | Dec-24 | Concrete | CO-05 | Post-Tension Works | Plaza Construction | PO-56346 | 74560 | 0 | Forecast | S. Patel
INV-CON-01-1842 | Jan-24 | Concrete | CO-06 | Concrete Repair | Plaza Construction | PO-47700 | 10560 | 10639.7 | Posted | R. Okafor
INV-CON-02-6761 | Feb-24 | Concrete | CO-06 | Concrete Repair | Plaza Construction | PO-23579 | 17600 | 17055.12 | Posted | A. Chen
INV-CON-03-3535 | Mar-24 | Concrete | CO-06 | Concrete Repair | Plaza Construction | PO-96079 | 21120 | 21065.58 | Posted | S. Patel
INV-CON-04-4674 | Apr-24 | Concrete | CO-06 | Concrete Repair | Plaza Construction | PO-24184 | 28160 | 26990.85 | Posted | R. Okafor
INV-CON-05-7022 | May-24 | Concrete | CO-06 | Concrete Repair | Plaza Construction | PO-25058 | 38720 | 36774.99 | Posted | R. Okafor
INV-CON-06-4705 | Jun-24 | Concrete | CO-06 | Concrete Repair | Plaza Construction | PO-66244 | 45760 | 47045.06 | Posted | J. Martinez
INV-CON-07-5381 | Jul-24 | Concrete | CO-06 | Concrete Repair | Plaza Construction | PO-13794 | 45760 | 43498.85 | Posted | A. Chen
INV-CON-08-5477 | Aug-24 | Concrete | CO-06 | Concrete Repair | Plaza Construction | PO-50499 | 42240 | 46397.47 | Posted | R. Okafor
INV-CON-09-6751 | Sep-24 | Concrete | CO-06 | Concrete Repair | Plaza Construction | PO-10800 | 38720 | 39190.71 | Posted | A. Chen
INV-CON-10-3347 | Oct-24 | Concrete | CO-06 | Concrete Repair | Plaza Construction | PO-84228 | 28160 | 0 | Forecast | S. Patel
INV-CON-11-2140 | Nov-24 | Concrete | CO-06 | Concrete Repair | Plaza Construction | PO-28595 | 21120 | 0 | Forecast | J. Martinez
INV-CON-12-2503 | Dec-24 | Concrete | CO-06 | Concrete Repair | Plaza Construction | PO-79531 | 14080 | 0 | Forecast | A. Chen
INV-CON-01-7878 | Jan-24 | Concrete | CO-07 | Waterproofing | Navillus Contracting | PO-69460 | 111900 | 108495.9 | Posted | R. Okafor
INV-CON-02-3578 | Feb-24 | Concrete | CO-07 | Waterproofing | Navillus Contracting | PO-58503 | 186500 | 174899.22 | Posted | R. Okafor
INV-CON-03-6314 | Mar-24 | Concrete | CO-07 | Waterproofing | Navillus Contracting | PO-84395 | 223800 | 211284.32 | Posted | J. Martinez
INV-CON-04-1861 | Apr-24 | Concrete | CO-07 | Waterproofing | Navillus Contracting | PO-30392 | 298400 | 273372.85 | Posted | A. Chen
INV-CON-05-1815 | May-24 | Concrete | CO-07 | Waterproofing | Navillus Contracting | PO-98338 | 410300 | 372187.63 | Posted | J. Martinez
INV-CON-06-5458 | Jun-24 | Concrete | CO-07 | Waterproofing | Navillus Contracting | PO-68079 | 484900 | 486177.48 | Posted | S. Patel
INV-CON-07-8957 | Jul-24 | Concrete | CO-07 | Waterproofing | Navillus Contracting | PO-89570 | 484900 | 446256.67 | Posted | S. Patel
INV-CON-08-7785 | Aug-24 | Concrete | CO-07 | Waterproofing | Navillus Contracting | PO-45804 | 447600 | 461472.22 | Posted | A. Chen
INV-CON-09-9394 | Sep-24 | Concrete | CO-07 | Waterproofing | Navillus Contracting | PO-24918 | 410300 | 412874.32 | Posted | R. Okafor
INV-CON-10-8043 | Oct-24 | Concrete | CO-07 | Waterproofing | Navillus Contracting | PO-24534 | 298400 | 0 | Forecast | R. Okafor
INV-CON-11-8972 | Nov-24 | Concrete | CO-07 | Waterproofing | Navillus Contracting | PO-79066 | 223800 | 0 | Forecast | R. Okafor
INV-CON-12-1744 | Dec-24 | Concrete | CO-07 | Waterproofing | Navillus Contracting | PO-38903 | 149200 | 0 | Forecast | S. Patel
INV-CON-01-1897 | Jan-24 | Concrete | CO-08 | Slab on Grade | Plaza Construction | PO-11007 | 48900 | 46568.8 | Posted | A. Chen
INV-CON-02-5938 | Feb-24 | Concrete | CO-08 | Slab on Grade | Plaza Construction | PO-37686 | 81500 | 82381.66 | Posted | A. Chen
INV-CON-03-5186 | Mar-24 | Concrete | CO-08 | Slab on Grade | Plaza Construction | PO-47938 | 97800 | 94072.1 | Posted | R. Okafor
INV-CON-04-2965 | Apr-24 | Concrete | CO-08 | Slab on Grade | Plaza Construction | PO-11013 | 130400 | 120717.59 | Posted | S. Patel
INV-CON-05-8055 | May-24 | Concrete | CO-08 | Slab on Grade | Plaza Construction | PO-33028 | 179300 | 172855.09 | Posted | A. Chen
INV-CON-06-7229 | Jun-24 | Concrete | CO-08 | Slab on Grade | Plaza Construction | PO-79806 | 211900 | 211330.26 | Posted | A. Chen
INV-CON-07-9196 | Jul-24 | Concrete | CO-08 | Slab on Grade | Plaza Construction | PO-83233 | 211900 | 211440.99 | Posted | R. Okafor
INV-CON-08-2180 | Aug-24 | Concrete | CO-08 | Slab on Grade | Plaza Construction | PO-62044 | 195600 | 210207.89 | Posted | J. Martinez
INV-CON-09-8147 | Sep-24 | Concrete | CO-08 | Slab on Grade | Plaza Construction | PO-12456 | 179300 | 179703.01 | Posted | S. Patel
INV-CON-10-2275 | Oct-24 | Concrete | CO-08 | Slab on Grade | Plaza Construction | PO-51033 | 130400 | 0 | Forecast | S. Patel
INV-CON-11-7626 | Nov-24 | Concrete | CO-08 | Slab on Grade | Plaza Construction | PO-93904 | 97800 | 0 | Forecast | S. Patel
INV-CON-12-5743 | Dec-24 | Concrete | CO-08 | Slab on Grade | Plaza Construction | PO-25096 | 65200 | 0 | Forecast | S. Patel
INV-CON-01-6321 | Jan-24 | Concrete | CO-09 | Precast Elements | Turner Specialty | PO-32527 | 88800 | 86864.47 | Posted | S. Patel
INV-CON-02-6928 | Feb-24 | Concrete | CO-09 | Precast Elements | Turner Specialty | PO-21551 | 148000 | 140361.58 | Posted | S. Patel
INV-CON-03-2734 | Mar-24 | Concrete | CO-09 | Precast Elements | Turner Specialty | PO-41891 | 177600 | 179016.74 | Posted | S. Patel
INV-CON-04-7560 | Apr-24 | Concrete | CO-09 | Precast Elements | Turner Specialty | PO-78676 | 236800 | 234913.38 | Posted | J. Martinez
INV-CON-05-7484 | May-24 | Concrete | CO-09 | Precast Elements | Turner Specialty | PO-50668 | 325600 | 322939.71 | Posted | R. Okafor
INV-CON-06-4630 | Jun-24 | Concrete | CO-09 | Precast Elements | Turner Specialty | PO-53655 | 384800 | 375569.26 | Posted | A. Chen
INV-CON-07-2251 | Jul-24 | Concrete | CO-09 | Precast Elements | Turner Specialty | PO-76910 | 384800 | 365264.67 | Posted | J. Martinez
INV-CON-08-9693 | Aug-24 | Concrete | CO-09 | Precast Elements | Turner Specialty | PO-76840 | 355200 | 383269.1 | Posted | A. Chen
INV-CON-09-6724 | Sep-24 | Concrete | CO-09 | Precast Elements | Turner Specialty | PO-56019 | 325600 | 311677.93 | Posted | A. Chen
INV-CON-10-4871 | Oct-24 | Concrete | CO-09 | Precast Elements | Turner Specialty | PO-23474 | 236800 | 0 | Forecast | A. Chen
INV-CON-11-5193 | Nov-24 | Concrete | CO-09 | Precast Elements | Turner Specialty | PO-35856 | 177600 | 0 | Forecast | A. Chen
INV-CON-12-3504 | Dec-24 | Concrete | CO-09 | Precast Elements | Turner Specialty | PO-95918 | 118400 | 0 | Forecast | J. Martinez
INV-FIT-02-9095 | Feb-24 | Fit-Out | FI-01 | Partitions & Drywall | Structure Tone | PO-70811 | 50250 | 51116.91 | Posted | S. Patel
INV-FIT-03-6295 | Mar-24 | Fit-Out | FI-01 | Partitions & Drywall | Structure Tone | PO-92210 | 100500 | 97884.55 | Posted | R. Okafor
INV-FIT-04-3473 | Apr-24 | Fit-Out | FI-01 | Partitions & Drywall | Structure Tone | PO-67640 | 201000 | 201689.22 | Posted | J. Martinez
INV-FIT-05-8682 | May-24 | Fit-Out | FI-01 | Partitions & Drywall | Structure Tone | PO-67961 | 301500 | 294720.39 | Posted | R. Okafor
INV-FIT-06-5500 | Jun-24 | Fit-Out | FI-01 | Partitions & Drywall | Structure Tone | PO-87518 | 402000 | 351829.42 | Posted | J. Martinez
INV-FIT-07-6766 | Jul-24 | Fit-Out | FI-01 | Partitions & Drywall | Structure Tone | PO-76497 | 603000 | 0 | Forecast | J. Martinez
INV-FIT-08-6085 | Aug-24 | Fit-Out | FI-01 | Partitions & Drywall | Structure Tone | PO-70521 | 703500 | 0 | Forecast | S. Patel
INV-FIT-09-1616 | Sep-24 | Fit-Out | FI-01 | Partitions & Drywall | Structure Tone | PO-17456 | 753750 | 0 | Forecast | R. Okafor
INV-FIT-10-5703 | Oct-24 | Fit-Out | FI-01 | Partitions & Drywall | Structure Tone | PO-20057 | 703500 | 0 | Forecast | J. Martinez
INV-FIT-11-9307 | Nov-24 | Fit-Out | FI-01 | Partitions & Drywall | Structure Tone | PO-60394 | 603000 | 0 | Forecast | S. Patel
INV-FIT-12-1672 | Dec-24 | Fit-Out | FI-01 | Partitions & Drywall | Structure Tone | PO-68947 | 603000 | 0 | Forecast | A. Chen
INV-FIT-02-8792 | Feb-24 | Fit-Out | FI-02 | Raised Access Flooring | Sciame Construction | PO-75715 | 12730 | 12166.77 | Posted | A. Chen
INV-FIT-03-2013 | Mar-24 | Fit-Out | FI-02 | Raised Access Flooring | Sciame Construction | PO-69050 | 25460 | 24306.8 | Posted | J. Martinez
INV-FIT-04-6626 | Apr-24 | Fit-Out | FI-02 | Raised Access Flooring | Sciame Construction | PO-21053 | 50920 | 49356.72 | Posted | A. Chen
INV-FIT-05-1641 | May-24 | Fit-Out | FI-02 | Raised Access Flooring | Sciame Construction | PO-42472 | 76380 | 75374.22 | Posted | S. Patel
INV-FIT-06-8199 | Jun-24 | Fit-Out | FI-02 | Raised Access Flooring | Sciame Construction | PO-78690 | 101840 | 91543.57 | Posted | A. Chen
INV-FIT-07-6962 | Jul-24 | Fit-Out | FI-02 | Raised Access Flooring | Sciame Construction | PO-58870 | 152760 | 0 | Forecast | R. Okafor
INV-FIT-08-7347 | Aug-24 | Fit-Out | FI-02 | Raised Access Flooring | Sciame Construction | PO-63578 | 178220 | 0 | Forecast | R. Okafor
INV-FIT-09-1857 | Sep-24 | Fit-Out | FI-02 | Raised Access Flooring | Sciame Construction | PO-92691 | 190950 | 0 | Forecast | R. Okafor
INV-FIT-10-2079 | Oct-24 | Fit-Out | FI-02 | Raised Access Flooring | Sciame Construction | PO-53213 | 178220 | 0 | Forecast | J. Martinez
INV-FIT-11-7333 | Nov-24 | Fit-Out | FI-02 | Raised Access Flooring | Sciame Construction | PO-47243 | 152760 | 0 | Forecast | R. Okafor
INV-FIT-12-3463 | Dec-24 | Fit-Out | FI-02 | Raised Access Flooring | Sciame Construction | PO-53694 | 152760 | 0 | Forecast | J. Martinez
INV-FIT-02-3317 | Feb-24 | Fit-Out | FI-03 | Suspended Ceilings | Hunter Roberts | PO-55851 | 18450 | 17791.32 | Posted | R. Okafor
INV-FIT-03-7421 | Mar-24 | Fit-Out | FI-03 | Suspended Ceilings | Hunter Roberts | PO-26901 | 36900 | 35971.73 | Posted | J. Martinez
INV-FIT-04-6072 | Apr-24 | Fit-Out | FI-03 | Suspended Ceilings | Hunter Roberts | PO-83259 | 73800 | 72805.64 | Posted | S. Patel
INV-FIT-05-6381 | May-24 | Fit-Out | FI-03 | Suspended Ceilings | Hunter Roberts | PO-26750 | 110700 | 100970.21 | Posted | J. Martinez
INV-FIT-06-7937 | Jun-24 | Fit-Out | FI-03 | Suspended Ceilings | Hunter Roberts | PO-76648 | 147600 | 129083.54 | Posted | R. Okafor
INV-FIT-07-1298 | Jul-24 | Fit-Out | FI-03 | Suspended Ceilings | Hunter Roberts | PO-57526 | 221400 | 0 | Forecast | R. Okafor
INV-FIT-08-3953 | Aug-24 | Fit-Out | FI-03 | Suspended Ceilings | Hunter Roberts | PO-38074 | 258300 | 0 | Forecast | R. Okafor
INV-FIT-09-8967 | Sep-24 | Fit-Out | FI-03 | Suspended Ceilings | Hunter Roberts | PO-35166 | 276750 | 0 | Forecast | A. Chen
INV-FIT-10-3253 | Oct-24 | Fit-Out | FI-03 | Suspended Ceilings | Hunter Roberts | PO-30308 | 258300 | 0 | Forecast | J. Martinez
INV-FIT-11-5846 | Nov-24 | Fit-Out | FI-03 | Suspended Ceilings | Hunter Roberts | PO-23256 | 221400 | 0 | Forecast | J. Martinez
INV-FIT-12-6517 | Dec-24 | Fit-Out | FI-03 | Suspended Ceilings | Hunter Roberts | PO-91006 | 221400 | 0 | Forecast | A. Chen
INV-FIT-02-7172 | Feb-24 | Fit-Out | FI-04 | Doors & Hardware | Hunter Roberts | PO-30218 | 34870 | 33380.22 | Posted | A. Chen
INV-FIT-03-3962 | Mar-24 | Fit-Out | FI-04 | Doors & Hardware | Hunter Roberts | PO-91885 | 69740 | 68385.42 | Posted | A. Chen
INV-FIT-04-8170 | Apr-24 | Fit-Out | FI-04 | Doors & Hardware | Hunter Roberts | PO-15726 | 139480 | 138797.75 | Posted | S. Patel
INV-FIT-05-6968 | May-24 | Fit-Out | FI-04 | Doors & Hardware | Hunter Roberts | PO-98652 | 209220 | 190437.93 | Posted | A. Chen
INV-FIT-06-8277 | Jun-24 | Fit-Out | FI-04 | Doors & Hardware | Hunter Roberts | PO-90031 | 278960 | 243983 | Posted | R. Okafor
INV-FIT-07-8355 | Jul-24 | Fit-Out | FI-04 | Doors & Hardware | Hunter Roberts | PO-40671 | 418440 | 0 | Forecast | A. Chen
INV-FIT-08-6070 | Aug-24 | Fit-Out | FI-04 | Doors & Hardware | Hunter Roberts | PO-71474 | 488180 | 0 | Forecast | A. Chen
INV-FIT-09-7026 | Sep-24 | Fit-Out | FI-04 | Doors & Hardware | Hunter Roberts | PO-98907 | 523050 | 0 | Forecast | S. Patel
INV-FIT-10-8564 | Oct-24 | Fit-Out | FI-04 | Doors & Hardware | Hunter Roberts | PO-46932 | 488180 | 0 | Forecast | S. Patel
INV-FIT-11-9239 | Nov-24 | Fit-Out | FI-04 | Doors & Hardware | Hunter Roberts | PO-79135 | 418440 | 0 | Forecast | S. Patel
INV-FIT-12-3655 | Dec-24 | Fit-Out | FI-04 | Doors & Hardware | Hunter Roberts | PO-36174 | 418440 | 0 | Forecast | A. Chen
INV-FIT-02-1854 | Feb-24 | Fit-Out | FI-05 | Glazing & Curtain Wall | Sciame Construction | PO-94040 | 15090 | 14900.27 | Posted | S. Patel
INV-FIT-03-7081 | Mar-24 | Fit-Out | FI-05 | Glazing & Curtain Wall | Sciame Construction | PO-82684 | 30180 | 28300.12 | Posted | J. Martinez
INV-FIT-04-9452 | Apr-24 | Fit-Out | FI-05 | Glazing & Curtain Wall | Sciame Construction | PO-26341 | 60360 | 60691.86 | Posted | R. Okafor
INV-FIT-05-2374 | May-24 | Fit-Out | FI-05 | Glazing & Curtain Wall | Sciame Construction | PO-31012 | 90540 | 89859.92 | Posted | R. Okafor
INV-FIT-06-8361 | Jun-24 | Fit-Out | FI-05 | Glazing & Curtain Wall | Sciame Construction | PO-77286 | 120720 | 115510.64 | Posted | A. Chen
INV-FIT-07-8167 | Jul-24 | Fit-Out | FI-05 | Glazing & Curtain Wall | Sciame Construction | PO-22021 | 181080 | 0 | Forecast | A. Chen
INV-FIT-08-8391 | Aug-24 | Fit-Out | FI-05 | Glazing & Curtain Wall | Sciame Construction | PO-55820 | 211260 | 0 | Forecast | J. Martinez
INV-FIT-09-7797 | Sep-24 | Fit-Out | FI-05 | Glazing & Curtain Wall | Sciame Construction | PO-16980 | 226350 | 0 | Forecast | S. Patel
INV-FIT-10-9224 | Oct-24 | Fit-Out | FI-05 | Glazing & Curtain Wall | Sciame Construction | PO-59015 | 211260 | 0 | Forecast | A. Chen
INV-FIT-11-7326 | Nov-24 | Fit-Out | FI-05 | Glazing & Curtain Wall | Sciame Construction | PO-20696 | 181080 | 0 | Forecast | R. Okafor
INV-FIT-12-4678 | Dec-24 | Fit-Out | FI-05 | Glazing & Curtain Wall | Sciame Construction | PO-13694 | 181080 | 0 | Forecast | R. Okafor
INV-FIT-02-6493 | Feb-24 | Fit-Out | FI-06 | Floor Finishes | Structure Tone | PO-29142 | 33220 | 32808.93 | Posted | A. Chen
INV-FIT-03-1627 | Mar-24 | Fit-Out | FI-06 | Floor Finishes | Structure Tone | PO-47601 | 66440 | 60489.14 | Posted | S. Patel
INV-FIT-04-3273 | Apr-24 | Fit-Out | FI-06 | Floor Finishes | Structure Tone | PO-71487 | 132880 | 133148.66 | Posted | S. Patel
INV-FIT-05-1086 | May-24 | Fit-Out | FI-06 | Floor Finishes | Structure Tone | PO-20384 | 199320 | 190459.91 | Posted | J. Martinez
INV-FIT-06-5193 | Jun-24 | Fit-Out | FI-06 | Floor Finishes | Structure Tone | PO-38266 | 265760 | 240668.34 | Posted | A. Chen
INV-FIT-07-9991 | Jul-24 | Fit-Out | FI-06 | Floor Finishes | Structure Tone | PO-89807 | 398640 | 0 | Forecast | S. Patel
INV-FIT-08-2821 | Aug-24 | Fit-Out | FI-06 | Floor Finishes | Structure Tone | PO-47762 | 465080 | 0 | Forecast | A. Chen
INV-FIT-09-5934 | Sep-24 | Fit-Out | FI-06 | Floor Finishes | Structure Tone | PO-25970 | 498300 | 0 | Forecast | J. Martinez
INV-FIT-10-4906 | Oct-24 | Fit-Out | FI-06 | Floor Finishes | Structure Tone | PO-65027 | 465080 | 0 | Forecast | S. Patel
INV-FIT-11-2029 | Nov-24 | Fit-Out | FI-06 | Floor Finishes | Structure Tone | PO-24530 | 398640 | 0 | Forecast | S. Patel
INV-FIT-12-9782 | Dec-24 | Fit-Out | FI-06 | Floor Finishes | Structure Tone | PO-12154 | 398640 | 0 | Forecast | A. Chen
INV-FIT-02-3352 | Feb-24 | Fit-Out | FI-07 | Painting & Decoration | Hunter Roberts | PO-48177 | 14700 | 14128.46 | Posted | S. Patel
INV-FIT-03-1025 | Mar-24 | Fit-Out | FI-07 | Painting & Decoration | Hunter Roberts | PO-90584 | 29400 | 27909.4 | Posted | R. Okafor
INV-FIT-04-4941 | Apr-24 | Fit-Out | FI-07 | Painting & Decoration | Hunter Roberts | PO-84798 | 58800 | 54528.59 | Posted | S. Patel
INV-FIT-05-4068 | May-24 | Fit-Out | FI-07 | Painting & Decoration | Hunter Roberts | PO-97080 | 88200 | 83527.41 | Posted | J. Martinez
INV-FIT-06-9576 | Jun-24 | Fit-Out | FI-07 | Painting & Decoration | Hunter Roberts | PO-57265 | 117600 | 102548.69 | Posted | J. Martinez
INV-FIT-07-9618 | Jul-24 | Fit-Out | FI-07 | Painting & Decoration | Hunter Roberts | PO-81313 | 176400 | 0 | Forecast | J. Martinez
INV-FIT-08-7397 | Aug-24 | Fit-Out | FI-07 | Painting & Decoration | Hunter Roberts | PO-71621 | 205800 | 0 | Forecast | J. Martinez
INV-FIT-09-7338 | Sep-24 | Fit-Out | FI-07 | Painting & Decoration | Hunter Roberts | PO-58929 | 220500 | 0 | Forecast | R. Okafor
INV-FIT-10-1266 | Oct-24 | Fit-Out | FI-07 | Painting & Decoration | Hunter Roberts | PO-56805 | 205800 | 0 | Forecast | J. Martinez
INV-FIT-11-6649 | Nov-24 | Fit-Out | FI-07 | Painting & Decoration | Hunter Roberts | PO-41604 | 176400 | 0 | Forecast | J. Martinez
INV-FIT-12-6447 | Dec-24 | Fit-Out | FI-07 | Painting & Decoration | Hunter Roberts | PO-27486 | 176400 | 0 | Forecast | J. Martinez
INV-FIT-02-9945 | Feb-24 | Fit-Out | FI-08 | Joinery Works | Sciame Construction | PO-54374 | 10900 | 10483.1 | Posted | A. Chen
INV-FIT-03-8612 | Mar-24 | Fit-Out | FI-08 | Joinery Works | Sciame Construction | PO-72722 | 21800 | 21019.01 | Posted | A. Chen
INV-FIT-04-3209 | Apr-24 | Fit-Out | FI-08 | Joinery Works | Sciame Construction | PO-18270 | 43600 | 43555.94 | Posted | S. Patel
INV-FIT-05-1605 | May-24 | Fit-Out | FI-08 | Joinery Works | Sciame Construction | PO-48462 | 65400 | 62647.97 | Posted | A. Chen
INV-FIT-06-1717 | Jun-24 | Fit-Out | FI-08 | Joinery Works | Sciame Construction | PO-36144 | 87200 | 83247.51 | Posted | J. Martinez
INV-FIT-07-6170 | Jul-24 | Fit-Out | FI-08 | Joinery Works | Sciame Construction | PO-50642 | 130800 | 0 | Forecast | S. Patel
INV-FIT-08-9897 | Aug-24 | Fit-Out | FI-08 | Joinery Works | Sciame Construction | PO-72049 | 152600 | 0 | Forecast | R. Okafor
INV-FIT-09-1599 | Sep-24 | Fit-Out | FI-08 | Joinery Works | Sciame Construction | PO-94790 | 163500 | 0 | Forecast | A. Chen
INV-FIT-10-5687 | Oct-24 | Fit-Out | FI-08 | Joinery Works | Sciame Construction | PO-56789 | 152600 | 0 | Forecast | J. Martinez
INV-FIT-11-6438 | Nov-24 | Fit-Out | FI-08 | Joinery Works | Sciame Construction | PO-45811 | 130800 | 0 | Forecast | J. Martinez
INV-FIT-12-7029 | Dec-24 | Fit-Out | FI-08 | Joinery Works | Sciame Construction | PO-67272 | 130800 | 0 | Forecast | S. Patel
INV-FIT-02-8204 | Feb-24 | Fit-Out | FI-09 | Signage & Wayfinding | Hunter Roberts | PO-60678 | 60910 | 59604.77 | Posted | R. Okafor
INV-FIT-03-4060 | Mar-24 | Fit-Out | FI-09 | Signage & Wayfinding | Hunter Roberts | PO-75038 | 121820 | 119994.76 | Posted | S. Patel
INV-FIT-04-7018 | Apr-24 | Fit-Out | FI-09 | Signage & Wayfinding | Hunter Roberts | PO-78062 | 243640 | 230983.05 | Posted | R. Okafor
INV-FIT-05-2353 | May-24 | Fit-Out | FI-09 | Signage & Wayfinding | Hunter Roberts | PO-65640 | 365460 | 363269.48 | Posted | J. Martinez
INV-FIT-06-8055 | Jun-24 | Fit-Out | FI-09 | Signage & Wayfinding | Hunter Roberts | PO-88964 | 487280 | 422951.29 | Posted | A. Chen
INV-FIT-07-9937 | Jul-24 | Fit-Out | FI-09 | Signage & Wayfinding | Hunter Roberts | PO-48504 | 730920 | 0 | Forecast | R. Okafor
INV-FIT-08-2680 | Aug-24 | Fit-Out | FI-09 | Signage & Wayfinding | Hunter Roberts | PO-20494 | 852740 | 0 | Forecast | R. Okafor
INV-FIT-09-5843 | Sep-24 | Fit-Out | FI-09 | Signage & Wayfinding | Hunter Roberts | PO-50173 | 913650 | 0 | Forecast | S. Patel
INV-FIT-10-7981 | Oct-24 | Fit-Out | FI-09 | Signage & Wayfinding | Hunter Roberts | PO-31842 | 852740 | 0 | Forecast | S. Patel
INV-FIT-11-6759 | Nov-24 | Fit-Out | FI-09 | Signage & Wayfinding | Hunter Roberts | PO-68606 | 730920 | 0 | Forecast | J. Martinez
INV-FIT-12-6776 | Dec-24 | Fit-Out | FI-09 | Signage & Wayfinding | Hunter Roberts | PO-90589 | 730920 | 0 | Forecast | S. Patel
INV-FIT-02-1939 | Feb-24 | Fit-Out | FI-10 | Furniture Fit-Out | Sciame Construction | PO-19835 | 37880 | 36149.49 | Posted | S. Patel
INV-FIT-03-6952 | Mar-24 | Fit-Out | FI-10 | Furniture Fit-Out | Sciame Construction | PO-77251 | 75760 | 74787.14 | Posted | A. Chen
INV-FIT-04-1510 | Apr-24 | Fit-Out | FI-10 | Furniture Fit-Out | Sciame Construction | PO-28714 | 151520 | 148141.23 | Posted | S. Patel
INV-FIT-05-1570 | May-24 | Fit-Out | FI-10 | Furniture Fit-Out | Sciame Construction | PO-26545 | 227280 | 226559.9 | Posted | J. Martinez
INV-FIT-06-4866 | Jun-24 | Fit-Out | FI-10 | Furniture Fit-Out | Sciame Construction | PO-94562 | 303040 | 264738.45 | Posted | R. Okafor
INV-FIT-07-6933 | Jul-24 | Fit-Out | FI-10 | Furniture Fit-Out | Sciame Construction | PO-60181 | 454560 | 0 | Forecast | J. Martinez
INV-FIT-08-3513 | Aug-24 | Fit-Out | FI-10 | Furniture Fit-Out | Sciame Construction | PO-99006 | 530320 | 0 | Forecast | S. Patel
INV-FIT-09-7077 | Sep-24 | Fit-Out | FI-10 | Furniture Fit-Out | Sciame Construction | PO-58760 | 568200 | 0 | Forecast | S. Patel
INV-FIT-10-2259 | Oct-24 | Fit-Out | FI-10 | Furniture Fit-Out | Sciame Construction | PO-85225 | 530320 | 0 | Forecast | A. Chen
INV-FIT-11-9674 | Nov-24 | Fit-Out | FI-10 | Furniture Fit-Out | Sciame Construction | PO-58096 | 454560 | 0 | Forecast | S. Patel
INV-FIT-12-6150 | Dec-24 | Fit-Out | FI-10 | Furniture Fit-Out | Sciame Construction | PO-95139 | 454560 | 0 | Forecast | R. Okafor
INV-PRE-01-2858 | Jan-24 | Preliminaries | PR-01 | Site Management Staff | AECOM | PO-13396 | 108560 | 107519.8 | Posted | A. Chen
INV-PRE-02-9176 | Feb-24 | Preliminaries | PR-01 | Site Management Staff | AECOM | PO-77861 | 108560 | 117259.31 | Posted | S. Patel
INV-PRE-03-2929 | Mar-24 | Preliminaries | PR-01 | Site Management Staff | AECOM | PO-44311 | 122130 | 120466.07 | Posted | R. Okafor
INV-PRE-04-8311 | Apr-24 | Preliminaries | PR-01 | Site Management Staff | AECOM | PO-38124 | 108560 | 112024.99 | Posted | R. Okafor
INV-PRE-05-9047 | May-24 | Preliminaries | PR-01 | Site Management Staff | AECOM | PO-36237 | 122130 | 122111.45 | Posted | J. Martinez
INV-PRE-06-3223 | Jun-24 | Preliminaries | PR-01 | Site Management Staff | AECOM | PO-19706 | 108560 | 111163.63 | Posted | S. Patel
INV-PRE-07-3828 | Jul-24 | Preliminaries | PR-01 | Site Management Staff | AECOM | PO-68341 | 108560 | 106326.54 | Posted | J. Martinez
INV-PRE-08-6236 | Aug-24 | Preliminaries | PR-01 | Site Management Staff | AECOM | PO-97535 | 122130 | 123167.75 | Posted | R. Okafor
INV-PRE-09-2063 | Sep-24 | Preliminaries | PR-01 | Site Management Staff | AECOM | PO-82089 | 108560 | 0 | Forecast | R. Okafor
INV-PRE-10-5914 | Oct-24 | Preliminaries | PR-01 | Site Management Staff | AECOM | PO-30644 | 108560 | 0 | Forecast | A. Chen
INV-PRE-11-6922 | Nov-24 | Preliminaries | PR-01 | Site Management Staff | AECOM | PO-76683 | 122130 | 0 | Forecast | A. Chen
INV-PRE-12-2988 | Dec-24 | Preliminaries | PR-01 | Site Management Staff | AECOM | PO-36342 | 108560 | 0 | Forecast | A. Chen
INV-PRE-01-9094 | Jan-24 | Preliminaries | PR-02 | Temporary Site Offices | AECOM | PO-13445 | 80080 | 85086.73 | Posted | R. Okafor
INV-PRE-02-7044 | Feb-24 | Preliminaries | PR-02 | Temporary Site Offices | AECOM | PO-71263 | 80080 | 79304.54 | Posted | A. Chen
INV-PRE-03-2412 | Mar-24 | Preliminaries | PR-02 | Temporary Site Offices | AECOM | PO-18617 | 90090 | 82008.68 | Posted | R. Okafor
INV-PRE-04-7523 | Apr-24 | Preliminaries | PR-02 | Temporary Site Offices | AECOM | PO-72739 | 80080 | 78102.08 | Posted | S. Patel
INV-PRE-05-7708 | May-24 | Preliminaries | PR-02 | Temporary Site Offices | AECOM | PO-85353 | 90090 | 90823.6 | Posted | J. Martinez
INV-PRE-06-3053 | Jun-24 | Preliminaries | PR-02 | Temporary Site Offices | AECOM | PO-51553 | 80080 | 85031.88 | Posted | J. Martinez
INV-PRE-07-8372 | Jul-24 | Preliminaries | PR-02 | Temporary Site Offices | AECOM | PO-71057 | 80080 | 76314.53 | Posted | R. Okafor
INV-PRE-08-3102 | Aug-24 | Preliminaries | PR-02 | Temporary Site Offices | AECOM | PO-82260 | 90090 | 87906.76 | Posted | A. Chen
INV-PRE-09-3114 | Sep-24 | Preliminaries | PR-02 | Temporary Site Offices | AECOM | PO-66704 | 80080 | 0 | Forecast | J. Martinez
INV-PRE-10-3034 | Oct-24 | Preliminaries | PR-02 | Temporary Site Offices | AECOM | PO-77908 | 80080 | 0 | Forecast | A. Chen
INV-PRE-11-5982 | Nov-24 | Preliminaries | PR-02 | Temporary Site Offices | AECOM | PO-31581 | 90090 | 0 | Forecast | A. Chen
INV-PRE-12-6286 | Dec-24 | Preliminaries | PR-02 | Temporary Site Offices | AECOM | PO-39552 | 80080 | 0 | Forecast | R. Okafor
INV-PRE-01-5653 | Jan-24 | Preliminaries | PR-03 | Plant & Equipment Hire | Cumming Group | PO-20336 | 53840 | 54528.68 | Posted | R. Okafor
INV-PRE-02-4216 | Feb-24 | Preliminaries | PR-03 | Plant & Equipment Hire | Cumming Group | PO-93238 | 53840 | 58483.89 | Posted | R. Okafor
INV-PRE-03-3050 | Mar-24 | Preliminaries | PR-03 | Plant & Equipment Hire | Cumming Group | PO-91922 | 60570 | 59858.12 | Posted | R. Okafor
INV-PRE-04-9740 | Apr-24 | Preliminaries | PR-03 | Plant & Equipment Hire | Cumming Group | PO-22245 | 53840 | 54965.79 | Posted | A. Chen
INV-PRE-05-3526 | May-24 | Preliminaries | PR-03 | Plant & Equipment Hire | Cumming Group | PO-32439 | 60570 | 59038.59 | Posted | R. Okafor
INV-PRE-06-1674 | Jun-24 | Preliminaries | PR-03 | Plant & Equipment Hire | Cumming Group | PO-13718 | 53840 | 54048.66 | Posted | J. Martinez
INV-PRE-07-1744 | Jul-24 | Preliminaries | PR-03 | Plant & Equipment Hire | Cumming Group | PO-94076 | 53840 | 51962.27 | Posted | R. Okafor
INV-PRE-08-4453 | Aug-24 | Preliminaries | PR-03 | Plant & Equipment Hire | Cumming Group | PO-84991 | 60570 | 55953.53 | Posted | S. Patel
INV-PRE-09-1496 | Sep-24 | Preliminaries | PR-03 | Plant & Equipment Hire | Cumming Group | PO-75278 | 53840 | 0 | Forecast | R. Okafor
INV-PRE-10-5949 | Oct-24 | Preliminaries | PR-03 | Plant & Equipment Hire | Cumming Group | PO-73300 | 53840 | 0 | Forecast | A. Chen
INV-PRE-11-7653 | Nov-24 | Preliminaries | PR-03 | Plant & Equipment Hire | Cumming Group | PO-48985 | 60570 | 0 | Forecast | S. Patel
INV-PRE-12-2195 | Dec-24 | Preliminaries | PR-03 | Plant & Equipment Hire | Cumming Group | PO-17852 | 53840 | 0 | Forecast | A. Chen
INV-PRE-01-7809 | Jan-24 | Preliminaries | PR-04 | Safety & Welfare | WSP | PO-73471 | 249120 | 264661.11 | Posted | S. Patel
INV-PRE-02-4342 | Feb-24 | Preliminaries | PR-04 | Safety & Welfare | WSP | PO-54589 | 249120 | 266549.3 | Posted | A. Chen
INV-PRE-03-6121 | Mar-24 | Preliminaries | PR-04 | Safety & Welfare | WSP | PO-51853 | 280260 | 281186.64 | Posted | R. Okafor
INV-PRE-04-7532 | Apr-24 | Preliminaries | PR-04 | Safety & Welfare | WSP | PO-27139 | 249120 | 258223.56 | Posted | R. Okafor
INV-PRE-05-9437 | May-24 | Preliminaries | PR-04 | Safety & Welfare | WSP | PO-83616 | 280260 | 275551.01 | Posted | J. Martinez
INV-PRE-06-6228 | Jun-24 | Preliminaries | PR-04 | Safety & Welfare | WSP | PO-41685 | 249120 | 259018.78 | Posted | S. Patel
INV-PRE-07-3007 | Jul-24 | Preliminaries | PR-04 | Safety & Welfare | WSP | PO-45058 | 249120 | 256947.5 | Posted | S. Patel
INV-PRE-08-5061 | Aug-24 | Preliminaries | PR-04 | Safety & Welfare | WSP | PO-28465 | 280260 | 280390.58 | Posted | J. Martinez
INV-PRE-09-1829 | Sep-24 | Preliminaries | PR-04 | Safety & Welfare | WSP | PO-48038 | 249120 | 0 | Forecast | S. Patel
INV-PRE-10-7850 | Oct-24 | Preliminaries | PR-04 | Safety & Welfare | WSP | PO-42541 | 249120 | 0 | Forecast | A. Chen
INV-PRE-11-6364 | Nov-24 | Preliminaries | PR-04 | Safety & Welfare | WSP | PO-85718 | 280260 | 0 | Forecast | R. Okafor
INV-PRE-12-4110 | Dec-24 | Preliminaries | PR-04 | Safety & Welfare | WSP | PO-30885 | 249120 | 0 | Forecast | S. Patel
INV-PRE-01-8648 | Jan-24 | Preliminaries | PR-05 | Insurances & Bonds | Cumming Group | PO-75373 | 70400 | 70336.86 | Posted | R. Okafor
INV-PRE-02-9148 | Feb-24 | Preliminaries | PR-05 | Insurances & Bonds | Cumming Group | PO-13037 | 70400 | 72678.77 | Posted | J. Martinez
INV-PRE-03-7442 | Mar-24 | Preliminaries | PR-05 | Insurances & Bonds | Cumming Group | PO-76249 | 79200 | 72873.48 | Posted | S. Patel
INV-PRE-04-4944 | Apr-24 | Preliminaries | PR-05 | Insurances & Bonds | Cumming Group | PO-38199 | 70400 | 72676.56 | Posted | R. Okafor
INV-PRE-05-1797 | May-24 | Preliminaries | PR-05 | Insurances & Bonds | Cumming Group | PO-16624 | 79200 | 78262.22 | Posted | R. Okafor
INV-PRE-06-9108 | Jun-24 | Preliminaries | PR-05 | Insurances & Bonds | Cumming Group | PO-88317 | 70400 | 69345.77 | Posted | S. Patel
INV-PRE-07-5681 | Jul-24 | Preliminaries | PR-05 | Insurances & Bonds | Cumming Group | PO-80345 | 70400 | 70713.66 | Posted | J. Martinez
INV-PRE-08-2761 | Aug-24 | Preliminaries | PR-05 | Insurances & Bonds | Cumming Group | PO-66482 | 79200 | 77464.39 | Posted | A. Chen
INV-PRE-09-5333 | Sep-24 | Preliminaries | PR-05 | Insurances & Bonds | Cumming Group | PO-57943 | 70400 | 0 | Forecast | S. Patel
INV-PRE-10-6995 | Oct-24 | Preliminaries | PR-05 | Insurances & Bonds | Cumming Group | PO-15930 | 70400 | 0 | Forecast | S. Patel
INV-PRE-11-1838 | Nov-24 | Preliminaries | PR-05 | Insurances & Bonds | Cumming Group | PO-84747 | 79200 | 0 | Forecast | A. Chen
INV-PRE-12-6939 | Dec-24 | Preliminaries | PR-05 | Insurances & Bonds | Cumming Group | PO-82512 | 70400 | 0 | Forecast | R. Okafor
INV-PRE-01-7329 | Jan-24 | Preliminaries | PR-06 | Quality Assurance | AECOM | PO-76093 | 150720 | 152296.78 | Posted | S. Patel
INV-PRE-02-5582 | Feb-24 | Preliminaries | PR-06 | Quality Assurance | AECOM | PO-91689 | 150720 | 150329.12 | Posted | J. Martinez
INV-PRE-03-3108 | Mar-24 | Preliminaries | PR-06 | Quality Assurance | AECOM | PO-22672 | 169560 | 164803.9 | Posted | S. Patel
INV-PRE-04-7114 | Apr-24 | Preliminaries | PR-06 | Quality Assurance | AECOM | PO-54444 | 150720 | 149138.25 | Posted | R. Okafor
INV-PRE-05-3363 | May-24 | Preliminaries | PR-06 | Quality Assurance | AECOM | PO-36090 | 169560 | 170306.82 | Posted | S. Patel
INV-PRE-06-9193 | Jun-24 | Preliminaries | PR-06 | Quality Assurance | AECOM | PO-15276 | 150720 | 152911.7 | Posted | J. Martinez
INV-PRE-07-1637 | Jul-24 | Preliminaries | PR-06 | Quality Assurance | AECOM | PO-27961 | 150720 | 154077.73 | Posted | R. Okafor
INV-PRE-08-8761 | Aug-24 | Preliminaries | PR-06 | Quality Assurance | AECOM | PO-78069 | 169560 | 164758.79 | Posted | S. Patel
INV-PRE-09-3440 | Sep-24 | Preliminaries | PR-06 | Quality Assurance | AECOM | PO-89463 | 150720 | 0 | Forecast | A. Chen
INV-PRE-10-6373 | Oct-24 | Preliminaries | PR-06 | Quality Assurance | AECOM | PO-90356 | 150720 | 0 | Forecast | R. Okafor
INV-PRE-11-3662 | Nov-24 | Preliminaries | PR-06 | Quality Assurance | AECOM | PO-61505 | 169560 | 0 | Forecast | R. Okafor
INV-PRE-12-6511 | Dec-24 | Preliminaries | PR-06 | Quality Assurance | AECOM | PO-76494 | 150720 | 0 | Forecast | S. Patel
INV-PRE-01-5911 | Jan-24 | Preliminaries | PR-07 | Environmental Compliance | Cumming Group | PO-72245 | 67760 | 69877.24 | Posted | J. Martinez
INV-PRE-02-7035 | Feb-24 | Preliminaries | PR-07 | Environmental Compliance | Cumming Group | PO-53416 | 67760 | 72948.91 | Posted | J. Martinez
INV-PRE-03-7824 | Mar-24 | Preliminaries | PR-07 | Environmental Compliance | Cumming Group | PO-86507 | 76230 | 72138.95 | Posted | R. Okafor
INV-PRE-04-1436 | Apr-24 | Preliminaries | PR-07 | Environmental Compliance | Cumming Group | PO-88238 | 67760 | 64464.09 | Posted | S. Patel
INV-PRE-05-5350 | May-24 | Preliminaries | PR-07 | Environmental Compliance | Cumming Group | PO-95929 | 76230 | 71023.73 | Posted | A. Chen
INV-PRE-06-1841 | Jun-24 | Preliminaries | PR-07 | Environmental Compliance | Cumming Group | PO-86483 | 67760 | 70357.42 | Posted | S. Patel
INV-PRE-07-3793 | Jul-24 | Preliminaries | PR-07 | Environmental Compliance | Cumming Group | PO-78712 | 67760 | 67718.03 | Posted | S. Patel
INV-PRE-08-3421 | Aug-24 | Preliminaries | PR-07 | Environmental Compliance | Cumming Group | PO-99224 | 76230 | 75192.84 | Posted | A. Chen
INV-PRE-09-1517 | Sep-24 | Preliminaries | PR-07 | Environmental Compliance | Cumming Group | PO-85047 | 67760 | 0 | Forecast | J. Martinez
INV-PRE-10-4125 | Oct-24 | Preliminaries | PR-07 | Environmental Compliance | Cumming Group | PO-12482 | 67760 | 0 | Forecast | S. Patel
INV-PRE-11-6139 | Nov-24 | Preliminaries | PR-07 | Environmental Compliance | Cumming Group | PO-64890 | 76230 | 0 | Forecast | A. Chen
INV-PRE-12-7765 | Dec-24 | Preliminaries | PR-07 | Environmental Compliance | Cumming Group | PO-36724 | 67760 | 0 | Forecast | S. Patel
INV-PRE-01-8726 | Jan-24 | Preliminaries | PR-08 | Site Security | Cumming Group | PO-18163 | 21120 | 21026.62 | Posted | A. Chen
INV-PRE-02-9498 | Feb-24 | Preliminaries | PR-08 | Site Security | Cumming Group | PO-37176 | 21120 | 21115.22 | Posted | R. Okafor
INV-PRE-03-8837 | Mar-24 | Preliminaries | PR-08 | Site Security | Cumming Group | PO-78875 | 23760 | 21601.82 | Posted | S. Patel
INV-PRE-04-6140 | Apr-24 | Preliminaries | PR-08 | Site Security | Cumming Group | PO-32699 | 21120 | 20544.39 | Posted | S. Patel
INV-PRE-05-9734 | May-24 | Preliminaries | PR-08 | Site Security | Cumming Group | PO-54869 | 23760 | 23440.9 | Posted | R. Okafor
INV-PRE-06-5331 | Jun-24 | Preliminaries | PR-08 | Site Security | Cumming Group | PO-89963 | 21120 | 21153.57 | Posted | S. Patel
INV-PRE-07-4150 | Jul-24 | Preliminaries | PR-08 | Site Security | Cumming Group | PO-42311 | 21120 | 20725.6 | Posted | R. Okafor
INV-PRE-08-5890 | Aug-24 | Preliminaries | PR-08 | Site Security | Cumming Group | PO-39473 | 23760 | 23896.27 | Posted | R. Okafor
INV-PRE-09-5735 | Sep-24 | Preliminaries | PR-08 | Site Security | Cumming Group | PO-37168 | 21120 | 0 | Forecast | S. Patel
INV-PRE-10-6194 | Oct-24 | Preliminaries | PR-08 | Site Security | Cumming Group | PO-72888 | 21120 | 0 | Forecast | R. Okafor
INV-PRE-11-5480 | Nov-24 | Preliminaries | PR-08 | Site Security | Cumming Group | PO-47721 | 23760 | 0 | Forecast | J. Martinez
INV-PRE-12-9899 | Dec-24 | Preliminaries | PR-08 | Site Security | Cumming Group | PO-59767 | 21120 | 0 | Forecast | S. Patel
INV-PRE-01-3399 | Jan-24 | Preliminaries | PR-09 | Waste Management | WSP | PO-48070 | 9920 | 10013.71 | Posted | J. Martinez
INV-PRE-02-5712 | Feb-24 | Preliminaries | PR-09 | Waste Management | WSP | PO-20358 | 9920 | 10306.4 | Posted | R. Okafor
INV-PRE-03-8247 | Mar-24 | Preliminaries | PR-09 | Waste Management | WSP | PO-95979 | 11160 | 10966.49 | Posted | R. Okafor
INV-PRE-04-8849 | Apr-24 | Preliminaries | PR-09 | Waste Management | WSP | PO-38047 | 9920 | 9694.65 | Posted | A. Chen
INV-PRE-05-9824 | May-24 | Preliminaries | PR-09 | Waste Management | WSP | PO-45537 | 11160 | 11045.22 | Posted | R. Okafor
INV-PRE-06-3249 | Jun-24 | Preliminaries | PR-09 | Waste Management | WSP | PO-24316 | 9920 | 10407.96 | Posted | A. Chen
INV-PRE-07-4972 | Jul-24 | Preliminaries | PR-09 | Waste Management | WSP | PO-16653 | 9920 | 10236.35 | Posted | A. Chen
INV-PRE-08-4814 | Aug-24 | Preliminaries | PR-09 | Waste Management | WSP | PO-16880 | 11160 | 10407.26 | Posted | J. Martinez
INV-PRE-09-7771 | Sep-24 | Preliminaries | PR-09 | Waste Management | WSP | PO-53292 | 9920 | 0 | Forecast | S. Patel
INV-PRE-10-2647 | Oct-24 | Preliminaries | PR-09 | Waste Management | WSP | PO-99285 | 9920 | 0 | Forecast | A. Chen
INV-PRE-11-1084 | Nov-24 | Preliminaries | PR-09 | Waste Management | WSP | PO-82135 | 11160 | 0 | Forecast | A. Chen
INV-PRE-12-7666 | Dec-24 | Preliminaries | PR-09 | Waste Management | WSP | PO-95575 | 9920 | 0 | Forecast | S. Patel
INV-PRE-01-4267 | Jan-24 | Preliminaries | PR-10 | Small Tools & Consumables | WSP | PO-47649 | 100480 | 107385.51 | Posted | R. Okafor
INV-PRE-02-5676 | Feb-24 | Preliminaries | PR-10 | Small Tools & Consumables | WSP | PO-94659 | 100480 | 104165.81 | Posted | J. Martinez
INV-PRE-03-2465 | Mar-24 | Preliminaries | PR-10 | Small Tools & Consumables | WSP | PO-95498 | 113040 | 105404.65 | Posted | A. Chen
INV-PRE-04-9767 | Apr-24 | Preliminaries | PR-10 | Small Tools & Consumables | WSP | PO-14888 | 100480 | 98818.53 | Posted | A. Chen
INV-PRE-05-7846 | May-24 | Preliminaries | PR-10 | Small Tools & Consumables | WSP | PO-33040 | 113040 | 115833.7 | Posted | J. Martinez
INV-PRE-06-7504 | Jun-24 | Preliminaries | PR-10 | Small Tools & Consumables | WSP | PO-74930 | 100480 | 101660.9 | Posted | A. Chen
INV-PRE-07-5742 | Jul-24 | Preliminaries | PR-10 | Small Tools & Consumables | WSP | PO-14910 | 100480 | 97524.8 | Posted | J. Martinez
INV-PRE-08-5888 | Aug-24 | Preliminaries | PR-10 | Small Tools & Consumables | WSP | PO-84443 | 113040 | 110729.7 | Posted | J. Martinez
INV-PRE-09-6489 | Sep-24 | Preliminaries | PR-10 | Small Tools & Consumables | WSP | PO-47298 | 100480 | 0 | Forecast | S. Patel
INV-PRE-10-9901 | Oct-24 | Preliminaries | PR-10 | Small Tools & Consumables | WSP | PO-78723 | 100480 | 0 | Forecast | S. Patel
INV-PRE-11-3198 | Nov-24 | Preliminaries | PR-10 | Small Tools & Consumables | WSP | PO-76088 | 113040 | 0 | Forecast | S. Patel
INV-PRE-12-5470 | Dec-24 | Preliminaries | PR-10 | Small Tools & Consumables | WSP | PO-35272 | 100480 | 0 | Forecast | J. Martinez

## Budget_Register
Trade | Cost_Code | Description | Original_Budget | Approved_Changes | Contingency | Contractor | Current_Budget
Civil | CI-01 | Site Preparation & Clearing | 1642000 | 83000 | 120000 | Judlau Contracting | 1725000
Civil | CI-02 | Earthworks & Grading | 1705000 | -16000 | 116000 | Judlau Contracting | 1689000
Civil | CI-03 | Dewatering Works | 663000 | 2000 | 49000 | Judlau Contracting | 665000
Civil | CI-04 | Underground Utilities | 2581000 | -28000 | 266000 | Judlau Contracting | 2553000
Civil | CI-05 | Piling & Foundations | 6485000 | 395000 | 731000 | Judlau Contracting | 6880000
Civil | CI-06 | Site Roads & Hardstanding | 1397000 | 20000 | 102000 | Posillico Civil | 1417000
Civil | CI-07 | Retaining Walls | 890000 | -13000 | 56000 | Tully Construction | 877000
Civil | CI-08 | Drainage & Stormwater | 1133000 | -33000 | 131000 | Tully Construction | 1100000
Civil | CI-09 | Site Hoarding & Fencing | 452000 | 24000 | 30000 | Tully Construction | 476000
Civil | CI-10 | Mobilization | 1553000 | 77000 | 110000 | Posillico Civil | 1630000
Structural Steel | ST-01 | Steel Fabrication | 3810000 | 36000 | 260000 | Banker Steel | 3846000
Structural Steel | ST-02 | Steel Erection | 4264000 | -72000 | 232000 | Supreme Steel | 4192000
Structural Steel | ST-03 | Connection Design | 7492000 | 341000 | 458000 | Schuff Steel | 7833000
Structural Steel | ST-04 | Fireproofing Steel | 2445000 | 112000 | 254000 | Schuff Steel | 2557000
Structural Steel | ST-05 | Secondary Steelwork | 2614000 | 6000 | 298000 | Schuff Steel | 2620000
Structural Steel | ST-06 | Steel Decking | 1315000 | 99000 | 86000 | Supreme Steel | 1414000
Structural Steel | ST-07 | Temporary Works Steel | 2431000 | 127000 | 148000 | Schuff Steel | 2558000
Structural Steel | ST-08 | Misc Metalwork | 337000 | 16000 | 26000 | Supreme Steel | 353000
Structural Steel | ST-09 | NDT Testing | 7492000 | 436000 | 772000 | Banker Steel | 7928000
MEP | ME-01 | Mechanical HVAC | 2359000 | 106000 | 244000 | Arden Building Products | 2465000
MEP | ME-02 | Plumbing & Drainage | 2398000 | -50000 | 266000 | Petrocelli Electric | 2348000
MEP | ME-03 | Electrical HV | 6065000 | 59000 | 527000 | Arden Building Products | 6124000
MEP | ME-04 | Electrical LV | 2821000 | 173000 | 163000 | Arden Building Products | 2994000
MEP | ME-05 | Fire Protection Systems | 2569000 | 75000 | 165000 | Forest Electric | 2644000
MEP | ME-06 | BMS Controls | 2184000 | 59000 | 159000 | Forest Electric | 2243000
MEP | ME-07 | Lifts & Escalators | 3275000 | 160000 | 320000 | Petrocelli Electric | 3435000
MEP | ME-08 | Generator Sets | 6727000 | 176000 | 379000 | Forest Electric | 6903000
MEP | ME-09 | Specialist Systems | 10752000 | 284000 | 879000 | Petrocelli Electric | 11036000
MEP | ME-10 | Testing & Commissioning MEP | 2650000 | 83000 | 237000 | Arden Building Products | 2733000
Concrete | CO-01 | Rebar Supply | 2108000 | 104000 | 224000 | Navillus Contracting | 2212000
Concrete | CO-02 | Rebar Fix | 1471000 | -44000 | 100000 | Turner Specialty | 1427000
Concrete | CO-03 | Formwork | 5905000 | -148000 | 534000 | Navillus Contracting | 5757000
Concrete | CO-04 | Ready-Mix Concrete | 5321000 | 157000 | 527000 | Turner Specialty | 5478000
Concrete | CO-05 | Post-Tension Works | 613000 | -14000 | 71000 | Navillus Contracting | 599000
Concrete | CO-06 | Concrete Repair | 2159000 | 32000 | 113000 | Turner Specialty | 2191000
Concrete | CO-07 | Waterproofing | 2329000 | 181000 | 241000 | Plaza Construction | 2510000
Concrete | CO-08 | Slab on Grade | 1449000 | 16000 | 170000 | Navillus Contracting | 1465000
Concrete | CO-09 | Precast Elements | 1245000 | 88000 | 101000 | Navillus Contracting | 1333000
Fit-Out | FI-01 | Partitions & Drywall | 1060000 | 48000 | 81000 | Hunter Roberts | 1108000
Fit-Out | FI-02 | Raised Access Flooring | 1385000 | -21000 | 154000 | Sciame Construction | 1364000
Fit-Out | FI-03 | Suspended Ceilings | 3557000 | 282000 | 207000 | Sciame Construction | 3839000
Fit-Out | FI-04 | Doors & Hardware | 2912000 | 146000 | 253000 | Structure Tone | 3058000
Fit-Out | FI-05 | Glazing & Curtain Wall | 2043000 | 109000 | 222000 | Sciame Construction | 2152000
Fit-Out | FI-06 | Floor Finishes | 1173000 | 58000 | 97000 | Sciame Construction | 1231000
Fit-Out | FI-07 | Painting & Decoration | 1401000 | 85000 | 122000 | Structure Tone | 1486000
Fit-Out | FI-08 | Joinery Works | 7782000 | -101000 | 640000 | Structure Tone | 7681000
Fit-Out | FI-09 | Signage & Wayfinding | 6227000 | 310000 | 720000 | Structure Tone | 6537000
Fit-Out | FI-10 | Furniture Fit-Out | 1361000 | 58000 | 71000 | Hunter Roberts | 1419000
Preliminaries | PR-01 | Site Management Staff | 587000 | 39000 | 61000 | AECOM | 626000
Preliminaries | PR-02 | Temporary Site Offices | 988000 | -22000 | 66000 | Cumming Group | 966000
Preliminaries | PR-03 | Plant & Equipment Hire | 1126000 | 40000 | 59000 | Cumming Group | 1166000
Preliminaries | PR-04 | Safety & Welfare | 507000 | -2000 | 56000 | AECOM | 505000
Preliminaries | PR-05 | Insurances & Bonds | 1762000 | -7000 | 138000 | AECOM | 1755000
Preliminaries | PR-06 | Quality Assurance | 1282000 | 71000 | 132000 | AECOM | 1353000
Preliminaries | PR-07 | Environmental Compliance | 1033000 | 2000 | 88000 | Cumming Group | 1035000
Preliminaries | PR-08 | Site Security | 869000 | 29000 | 78000 | Cumming Group | 898000
Preliminaries | PR-09 | Waste Management | 2469000 | -10000 | 265000 | AECOM | 2459000
Preliminaries | PR-10 | Small Tools & Consumables | 776000 | 21000 | 92000 | WSP | 797000

## Monthly_Planned_vs_Actual
Month | Month_No | Trade | Approved_Budget | Planned_Cumulative | Planned_Monthly | Actual_Cumulative | Data_Available
Jan-24 | 1 | Civil | 18500000 | 740000 | 740000 | 832500 | Yes
Feb-24 | 2 | Civil | 18500000 | 1665000 | 925000 | 1813000 | Yes
Mar-24 | 3 | Civil | 18500000 | 2775000 | 1110000 | 2997000 | Yes
Apr-24 | 4 | Civil | 18500000 | 4255000 | 1480000 | 4643500 | Yes
May-24 | 5 | Civil | 18500000 | 6290000 | 2035000 | 6882000 | Yes
Jun-24 | 6 | Civil | 18500000 | 8695000 | 2405000 | 9490500 | Yes
Jul-24 | 7 | Civil | 18500000 | 11100000 | 2405000 | 11858500 | Yes
Aug-24 | 8 | Civil | 18500000 | 13320000 | 2220000 | 14060000 | Yes
Sep-24 | 9 | Civil | 18500000 | 15170000 | 1850000 | 15891500 | Yes
Oct-24 | 10 | Civil | 18500000 | 16650000 | 1480000 |  | No
Nov-24 | 11 | Civil | 18500000 | 17760000 | 1110000 |  | No
Dec-24 | 12 | Civil | 18500000 | 18500000 | 740000 |  | No
Jan-24 | 1 | Structural Steel | 32200000 | 644000 | 644000 | 676200 | Yes
Feb-24 | 2 | Structural Steel | 32200000 | 1610000 | 966000 | 1738800 | Yes
Mar-24 | 3 | Structural Steel | 32200000 | 3220000 | 1610000 | 3542000 | Yes
Apr-24 | 4 | Structural Steel | 32200000 | 5796000 | 2576000 | 6375600 | Yes
May-24 | 5 | Structural Steel | 32200000 | 9338000 | 3542000 | 10336200 | Yes
Jun-24 | 6 | Structural Steel | 32200000 | 13846000 | 4508000 | 15198400 | Yes
Jul-24 | 7 | Structural Steel | 32200000 | 18676000 | 4830000 | 20447000 | Yes
Aug-24 | 8 | Structural Steel | 32200000 | 22540000 | 3864000 | 24922800 | Yes
Sep-24 | 9 | Structural Steel | 32200000 | 26082000 | 3542000 |  | No
Oct-24 | 10 | Structural Steel | 32200000 | 28658000 | 2576000 |  | No
Nov-24 | 11 | Structural Steel | 32200000 | 30590000 | 1932000 |  | No
Dec-24 | 12 | Structural Steel | 32200000 | 32200000 | 1610000 |  | No
Jan-24 | 1 | MEP | 41800000 | 418000 | 418000 | 418000 | Yes
Feb-24 | 2 | MEP | 41800000 | 1254000 | 836000 | 1337600 | Yes
Mar-24 | 3 | MEP | 41800000 | 2926000 | 1672000 | 3260400 | Yes
Apr-24 | 4 | MEP | 41800000 | 5434000 | 2508000 | 6061000 | Yes
May-24 | 5 | MEP | 41800000 | 9196000 | 3762000 | 10366400 | Yes
Jun-24 | 6 | MEP | 41800000 | 14212000 | 5016000 | 15967600 | Yes
Jul-24 | 7 | MEP | 41800000 | 20064000 | 5852000 | 22572000 | Yes
Aug-24 | 8 | MEP | 41800000 | 25916000 | 5852000 |  | No
Sep-24 | 9 | MEP | 41800000 | 31350000 | 5434000 |  | No
Oct-24 | 10 | MEP | 41800000 | 35530000 | 4180000 |  | No
Nov-24 | 11 | MEP | 41800000 | 38874000 | 3344000 |  | No
Dec-24 | 12 | MEP | 41800000 | 41800000 | 2926000 |  | No
Jan-24 | 1 | Concrete | 22600000 | 678000 | 678000 | 678000 | Yes
Feb-24 | 2 | Concrete | 22600000 | 1808000 | 1130000 | 1785400 | Yes
Mar-24 | 3 | Concrete | 22600000 | 3164000 | 1356000 | 3118800 | Yes
Apr-24 | 4 | Concrete | 22600000 | 4972000 | 1808000 | 4859000 | Yes
May-24 | 5 | Concrete | 22600000 | 7458000 | 2486000 | 7209400 | Yes
Jun-24 | 6 | Concrete | 22600000 | 10396000 | 2938000 | 10102200 | Yes
Jul-24 | 7 | Concrete | 22600000 | 13334000 | 2938000 | 12927200 | Yes
Aug-24 | 8 | Concrete | 22600000 | 16046000 | 2712000 | 15774800 | Yes
Sep-24 | 9 | Concrete | 22600000 | 18532000 | 2486000 | 18193000 | Yes
Oct-24 | 10 | Concrete | 22600000 | 20340000 | 1808000 |  | No
Nov-24 | 11 | Concrete | 22600000 | 21696000 | 1356000 |  | No
Dec-24 | 12 | Concrete | 22600000 | 22600000 | 904000 |  | No
Jan-24 | 1 | Fit-Out | 28900000 | 0 | 0 |  | Yes
Feb-24 | 2 | Fit-Out | 28900000 | 289000 | 289000 | 289000 | Yes
Mar-24 | 3 | Fit-Out | 28900000 | 867000 | 578000 | 838100 | Yes
Apr-24 | 4 | Fit-Out | 28900000 | 2023000 | 1156000 | 1965200 | Yes
May-24 | 5 | Fit-Out | 28900000 | 3757000 | 1734000 | 3612500 | Yes
Jun-24 | 6 | Fit-Out | 28900000 | 6069000 | 2312000 | 5722200 | Yes
Jul-24 | 7 | Fit-Out | 28900000 | 9537000 | 3468000 |  | No
Aug-24 | 8 | Fit-Out | 28900000 | 13583000 | 4046000 |  | No
Sep-24 | 9 | Fit-Out | 28900000 | 17918000 | 4335000 |  | No
Oct-24 | 10 | Fit-Out | 28900000 | 21964000 | 4046000 |  | No
Nov-24 | 11 | Fit-Out | 28900000 | 25432000 | 3468000 |  | No
Dec-24 | 12 | Fit-Out | 28900000 | 28900000 | 3468000 |  | No
Jan-24 | 1 | Preliminaries | 11400000 | 912000 | 912000 | 934800 | Yes
Feb-24 | 2 | Preliminaries | 11400000 | 1824000 | 912000 | 1881000 | Yes
Mar-24 | 3 | Preliminaries | 11400000 | 2850000 | 1026000 | 2861400 | Yes
Apr-24 | 4 | Preliminaries | 11400000 | 3762000 | 912000 | 3762000 | Yes
May-24 | 5 | Preliminaries | 11400000 | 4788000 | 1026000 | 4765200 | Yes
Jun-24 | 6 | Preliminaries | 11400000 | 5700000 | 912000 | 5688600 | Yes
Jul-24 | 7 | Preliminaries | 11400000 | 6612000 | 912000 | 6589200 | Yes
Aug-24 | 8 | Preliminaries | 11400000 | 7638000 | 1026000 | 7581000 | Yes
Sep-24 | 9 | Preliminaries | 11400000 | 8550000 | 912000 |  | No
Oct-24 | 10 | Preliminaries | 11400000 | 9462000 | 912000 |  | No
Nov-24 | 11 | Preliminaries | 11400000 | 10488000 | 1026000 |  | No
Dec-24 | 12 | Preliminaries | 11400000 | 11400000 | 912000 |  | No